## Summary
AI Software Engineer - 2026 sprint plan
28 Sep 2026 -> 31 Dec 2026. Tick tasks in 'Daily Plan' column L (choose ☑). Every number on this page is a formula over the other sheets.
How to use: only edit the blue/yellow cells - Done (☐/☑) in Daily Plan / Projects / Papers, Status in Projects, and Notes. Excel 365 users may convert the Done column to native checkboxes (Insert > Checkbox); the formulas count both.
Overall progress
Start date | 2026-09-28
End date | 2026-12-31
Study days | 82
Tasks planned | 167
Tasks done | 0
Tasks done (%) | 0%
Hours planned | 290
Hours done | 0
Hours done (%) | 0%
Tasks scheduled up to today | 3
Ahead (+) / behind (-) in tasks | -3
Projects done | 0
Papers read | 0
Assumptions: 3.5 h Mon-Fri, 4.0 h Sat, Sunday rest; 25 Dec is a 0-hour buffer. Source: plan design (tools/plan_data.py).
Progress by phase
Phase | Code | Tasks | Done | Done % | Hours | Hours done
Phase 0 - ML/DL revision | P0 | 8 | 0 | 0% | 10.5 | 0
Phase 1 - Transformers | P1 | 19 | 0 | 0% | 34 | 0
Phase 2 - LLMs & language modeling | P2 | 16 | 0 | 0% | 30 | 0
Phase 3 - Embeddings & information retrieval | P3 | 11 | 0 | 0% | 19 | 0
Phase 4 - RAG | P4 | 13 | 0 | 0% | 20.5 | 0
Phase 5 - LLM evaluation | P5 | 12 | 0 | 0% | 20 | 0
Phase 6 - Fine-tuning & post-training | P6 | 12 | 0 | 0% | 22 | 0
Phase 7 - AI agents | P7 | 11 | 0 | 0% | 18 | 0
Phase 8 - MCP | P8 | 2 | 0 | 0% | 3.5 | 0
Phase 9 - Inference & GPU optimization | P9 | 12 | 0 | 0% | 19 | 0
Phase 10 - Multimodal AI | P10 | 8 | 0 | 0% | 14.5 | 0
Phase 11 - Advanced LLM training (distributed, data, scaling) | P11 | 5 | 0 | 0% | 8.5 | 0
Phase 12 - RL for AI | P12 | 10 | 0 | 0% | 15 | 0
Phase 13 - Research skills (paper reading + reproductions) | P13 | 18 | 0 | 0% | 28.5 | 0
Capstone - AI Software Engineer | CAP | 10 | 0 | 0% | 27 | 0
Progress by week
Week focus | Week | Starts | Tasks | Done | Done % | Hours
Diagnostic revision -> attention from scratch | W1 | 2026-09-28 | 15 | 0 | 0% | 21.5
The modern Transformer block (Llama-style) + encoder-decoder | W2 | 2026-10-05 | 13 | 0 | 0% | 21.5
Tokenization + training a small GPT (CS336 Assignment 1) | W3 | 2026-10-12 | 11 | 0 | 0% | 21.5
Inside inference: KV cache, sampling, scaling laws, MoE | W4 | 2026-10-19 | 13 | 0 | 0% | 21.5
Embeddings, contrastive learning and vector search internals | W5 | 2026-10-26 | 12 | 0 | 0% | 21.5
RAG: beginner -> advanced -> research level | W6 | 2026-11-02 | 14 | 0 | 0% | 21.5
Evaluation like a professional AI team | W7 | 2026-11-09 | 13 | 0 | 0% | 21.5
Fine-tuning: SFT, chat templates, LoRA and QLoRA | W8 | 2026-11-16 | 11 | 0 | 0% | 21.5
RL for LLMs: RLHF, DPO, RLVR/GRPO and reasoning models | W9 | 2026-11-23 | 13 | 0 | 0% | 21.5
Agents from first principles + MCP | W10 | 2026-11-30 | 13 | 0 | 0% | 21.5
GPUs and LLM inference optimization | W11 | 2026-12-07 | 14 | 0 | 0% | 21.5
Distributed training & data (working knowledge) + multimodal AI | W12 | 2026-12-14 | 12 | 0 | 0% | 21.5
Capstone build: AI Software Engineer (integration) | W13 | 2026-12-21 | 7 | 0 | 0% | 18
Capstone hardening, final assessment, 2027 plan | W14 | 2026-12-28 | 6 | 0 | 0% | 14
What you already know (skip or quick revision only)
Topic | Action in this plan
Software engineering (design, testing, code review) | Skip
Backend / API development (FastAPI, REST, async) | Skip
Cloud, infrastructure, DevOps | Skip
Docker / Kubernetes | Skip - used for sandboxes & serving only
Databases (Postgres etc.) | Skip - pgvector is the only new part
CI/CD | Skip - reused for eval regression gates
Python (advanced) | Skip
PyTorch working knowledge | Revise - einops, profiler, autograd internals (W1)
Probability & statistics basics | Revise - MLE -> cross-entropy, bootstrap CIs (W1, W7)
Linear algebra | Revise - matrix calculus for backprop, low-rank (W1, W8)
Optimization (SGD, Adam) | Revise - implement AdamW + schedules (W1, W3)
Classical ML | Skip - only evaluation metrics & calibration revisited (W1)
Bias / variance, regularization | Revise - 1 hour incl. double descent (W1)
Model evaluation (P/R/F1, ROC, calibration) | Revise - 1 hour (W1)
Backpropagation | Revise - manual backward of an MLP + LayerNorm (W1)
Neural networks / CNN basics | Revise - CNN only as contrast for ViT (W12)
What you are learning (target level) and deferred items
MASTER = implement + explain without notes; WORKING = explain + use a library + one experiment; DEFER-2027 = scheduled in the 2027 continuation plan.
Topic | Phase | Target level | When | Self-rating (1-5)
Q/K/V, scaled dot-product, self/cross/causal attention, masking, MHA | P1 | MASTER | W1
Embeddings, positional encoding, residuals, LayerNorm vs RMSNorm | P1 | MASTER | W2
FFN vs SwiGLU, RoPE, GQA/MQA | P1 | MASTER | W2
Encoder vs decoder vs encoder-decoder; decoder-only LLMs | P1 | MASTER | W2
Mixture of Experts (routing, load balancing) | P1 | WORKING | W4
Tokenization: BPE, byte-level BPE, SentencePiece/unigram, vocab trade-offs | P2 | MASTER | W3
Next-token prediction, cross-entropy, teacher forcing, perplexity | P2 | MASTER | W3
Training dynamics: AdamW, warmup + cosine, clipping, instability | P2 | MASTER | W3
KV cache, prefill vs decode, context windows | P2 | MASTER | W4
Sampling: temperature, top-k, top-p, min-p, beam search, logits | P2 | MASTER | W4
Scaling laws, Chinchilla, model/data/compute trade-offs | P2/P11 | WORKING | W4
Embeddings, cosine similarity, contrastive learning (InfoNCE) | P3 | MASTER | W5
Sparse retrieval: TF-IDF, BM25 | P3 | MASTER | W5
ANN: IVF, product quantization, HNSW | P3 | MASTER | W5
Vector DBs: FAISS, pgvector, Qdrant | P3 | WORKING | W5
RAG pipeline: parsing, chunking, retrieval, context construction, generation | P4 | MASTER | W6
Hybrid search, reranking, query rewriting, multi-query, HyDE, parent-child | P4 | MASTER | W6
Context compression, metadata filtering, multi-vector retrieval | P4 | WORKING | W6
Agentic RAG, Graph RAG, long-context retrieval, retrieval planning | P4 | WORKING | W6
IR metrics: Recall@K, Precision@K, MRR, nDCG | P4/P5 | MASTER | W5, W7
Faithfulness, groundedness, context & answer relevance | P5 | MASTER | W7
Golden datasets, error analysis, LLM-as-judge (pairwise, rubric), calibration | P5 | MASTER | W7
Human evaluation, A/B testing, regression testing, statistics | P5 | WORKING | W7
Tool-call & agent evaluation | P5/P7 | WORKING | W7, W10
Pretraining vs continued pretraining vs instruction tuning / SFT | P6 | MASTER | W8
Chat templates, loss masking, dataset preparation | P6 | MASTER | W8
LoRA, QLoRA, PEFT/adapters | P6 | MASTER | W8
RLHF: reward models, PPO | P6/P12 | WORKING | W9
DPO (+ ORPO/KTO/SimPO awareness) | P6 | MASTER | W9
MDPs, policy gradients, advantage, actor-critic | P12 | WORKING | W9
RLVR, GRPO, reasoning models, reward hacking | P6/P12 | WORKING | W9
Tool/function calling, agent loops, ReAct | P7 | MASTER | W10
Planning, reflection, self-correction, memory, state | P7 | MASTER | W10
Multi-agent, human-in-the-loop, agent security | P7 | WORKING | W10
LangGraph: StateGraph, reducers, checkpointers, interrupts, streaming (P8 built on it) | P7 | MASTER | W10
LangChain 1.0: create_agent, middleware, tools, structured output, retrievers; LangSmith tracing/evals | P7/P4 | WORKING | W6, W10
smolagents, OpenAI Agents SDK, LlamaIndex (Workflows + RAG abstractions) | P7/P4 | WORKING | W6, W10
MCP architecture, client/server, tools/resources/prompts, transports, auth | P8 | MASTER | W10
GPU architecture, memory hierarchy, FLOPs, bandwidth, arithmetic intensity | P9 | MASTER | W11
CUDA programming model + Triton basics | P9 | WORKING | W11
Batching, continuous batching, TTFT/TPOT, throughput vs latency | P9 | MASTER | W11
Quantization: FP16/BF16/FP8/INT8/INT4, GPTQ, AWQ | P9 | WORKING | W11
FlashAttention, PagedAttention, speculative decoding | P9 | WORKING | W11
vLLM (hands-on), TensorRT-LLM (overview) | P9 | WORKING | W11
Distributed training: DP, ZeRO/FSDP, TP, PP, checkpointing | P11 | WORKING | W12
Data: construction, filtering, dedup, mixtures, synthetic data | P11 | WORKING | W12
ViT, CLIP, image embeddings, vision encoders | P10 | WORKING | W12
VLM architecture: projection layers, alignment, training, fine-tuning | P10 | WORKING | W12
OCR/document understanding, tables, charts, image RAG | P10 | WORKING | W12
Audio: speech-to-text (Whisper), TTS; video understanding | P10 | WORKING | W12
Paper reading (3-pass) + 6 small reproductions | P13 | MASTER | W1-W12
AI Software Engineer capstone (integration of everything) | CAP | MASTER | W13-W14
Writing CUDA kernels; FlashAttention-2 in Triton (CS336 A2) | P9 | DEFER-2027 | Q1 2027
TensorRT-LLM engines / SGLang internals in depth | P9 | DEFER-2027 | Q1 2027
Implementing TP/PP/context parallelism from scratch (picotron) | P11 | DEFER-2027 | Q1 2027
Pretraining data pipeline at scale (CS336 A4) | P11 | DEFER-2027 | Q1 2027
Full scaling-law study (CS336 A3) | P11 | DEFER-2027 | Q1 2027
Full RLHF-PPO trainer; RL at scale (verl); CS336 A5 full | P12 | DEFER-2027 | Q1 2027
Training a VLM from scratch; video models; TTS training | P10 | DEFER-2027 | Q2 2027
Long-context methods (YaRN, ring attention), SSMs/linear attention | P1 | DEFER-2027 | Q2 2027
Full reproduction of a 2026 paper + public write-up | P13 | DEFER-2027 | Q1-Q2 2027
LangGraph deployment / durable agents in production; other frameworks only if a job needs them | P7 | DEFER-2027 | Q1 2027
Example: rate 'KV cache, prefill vs decode' as 4 once you can derive the memory formula close-book.

## Daily Plan
# | Date | Day | Week | Phase | Type | Topic | Description | Link | Hours | Deliverable / assignment | Done | Notes
1 | 2026-09-28 | Mon | W1 | P0 | Setup | Workspace + GPU plan | Create one monorepo for all 2026 projects (uv, pytest, ruff, wandb or tensorboard). Decide compute: Mac/Colab for small runs, rented A10/L4/4090 by the hour for training weeks. | https://pytorch.org/get-started/locally/ | 0.5 | Repo skeleton | ☐
2 | 2026-09-28 | Mon | W1 | P0 | Review | Diagnostic self-test | Take the Phase 0 self-test in the checkpoints file. Anything you answer confidently in <2 min is skipped this week. | https://github.com/anshu8830/anshu/blob/main/curriculum/08-skill-checkpoints.md | 1 | List of gaps | ☐
3 | 2026-09-28 | Mon | W1 | P0 | Reading | Probability -> MLE -> cross-entropy; optimizers | UDL ch. 5 (loss functions as MLE) and ch. 6 (SGD, momentum, Adam). Then implement AdamW from scratch and match PyTorch. | https://udlbook.github.io/udlbook/ | 2 | adamw.py + test | ☐
4 | 2026-09-29 | Tue | W1 | P0 | Video | Backprop by hand | Backprop Ninja (skip if diagnostic passed). Exercise: manual backward for Linear->LayerNorm->GELU->Linear->softmax-CE; verify with torch.autograd.gradcheck. | https://www.youtube.com/watch?v=q8SA3rM6ckI | 2 | manual_backward.py | ☐
5 | 2026-09-29 | Tue | W1 | P0 | Reading | Matrix calculus refresh | Parr & Howard sections on vector chain rule + UDL ch. 7. Derive dL/dlogits = softmax - onehot and the LayerNorm backward on paper. | https://explained.ai/matrix-calculus/ | 1.5 | 1-page derivation | ☐
6 | 2026-09-30 | Wed | W1 | P0 | Video | PyTorch + resource accounting | CS336 L2 (trace + video in 2026 playlist): tensors, einops, FLOPs and memory accounting. Exercise: FLOPs of a (B,T,d)x(d,4d) matmul; memory of a 1B model in fp32/bf16 incl. Adam states. | https://cs336.stanford.edu/lectures/?trace=lecture_02 | 1.5 | accounting.md | ☐
7 | 2026-09-30 | Wed | W1 | P0 | Reading | Generalization revision | UDL ch. 8-9: bias/variance, double descent, weight decay, dropout, early stopping. 1 hour max. | https://udlbook.github.io/udlbook/ | 1 |  | ☐
8 | 2026-09-30 | Wed | W1 | P0 | Code | Evaluation revision | Implement precision/recall/F1, ROC-AUC vs PR-AUC and expected calibration error (ECE) on a toy classifier. | https://udlbook.github.io/udlbook/ | 1 | metrics.py | ☐
9 | 2026-10-01 | Thu | W1 | P1 | Video | Attention intuition | 3Blue1Brown DL5 + DL6 back to back. | https://www.youtube.com/watch?v=eMlx5fFNoYc | 1 |  | ☐
10 | 2026-10-01 | Thu | W1 | P1 | Reading | Illustrated Transformer | Read end-to-end; sketch the encoder/decoder data flow yourself. | https://jalammar.github.io/illustrated-transformer/ | 1 | Hand-drawn diagram | ☐
11 | 2026-10-01 | Thu | W1 | P13 | Paper | Attention Is All You Need (3-pass) | Read Keshav (15 min), then the paper: 3.1-3.2.3, 3.5, Table 3. Write notes with tensor shapes. | https://arxiv.org/abs/1706.03762 | 1.5 | Paper notes #1 | ☐
12 | 2026-10-02 | Fri | W1 | P1 | Reading | Math -> tensor shapes | Work through the attention concept note; fill every shape in the table yourself before reading the answer. | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/01-attention-and-transformer.md | 1 |  | ☐
13 | 2026-10-02 | Fri | W1 | P1 | Code | Scaled dot-product attention | Implement SDPA with causal + padding masks. Tests: equals F.scaled_dot_product_attention (atol 1e-6); perturbing future tokens does not change past outputs. | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/01-attention-and-transformer.md | 2.5 | P1: sdpa + tests | ☐
14 | 2026-10-03 | Sat | W1 | P1 | Code | Multi-head + cross attention | Fused QKV projection, split heads with view/transpose (or einops), output projection; cross-attention variant. Test against nn.MultiheadAttention with copied weights. | https://nlp.seas.harvard.edu/annotated-transformer/ | 2.5 | P1: mha.py | ☐
15 | 2026-10-03 | Sat | W1 | P1 | Experiment | Attention experiments | (a) remove 1/sqrt(d_k): plot softmax entropy vs d_k; (b) visualize attention maps on a toy sequence; (c) measure attention-matrix memory vs T. | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/01-attention-and-transformer.md | 1.5 | P1 notebook (DONE) | ☐
16 | 2026-10-05 | Mon | W2 | P1 | Video | Let's build GPT (code along) | Watch at 1.25x and type the code; stop at each stage and predict the next change before Karpathy makes it. | https://www.youtube.com/watch?v=kCc8FmEb1nY | 2.5 | gpt_karpathy.py | ☐
17 | 2026-10-05 | Mon | W2 | P1 | Reading | Annotated Transformer skim | Skim the encoder-decoder parts you will need on Saturday. | https://nlp.seas.harvard.edu/annotated-transformer/ | 1 |  | ☐
18 | 2026-10-06 | Tue | W2 | P1 | Video | CS336 L3 - Architectures | Video + slides: pre vs post norm, RMSNorm, SwiGLU, RoPE, parallel layers, d_ff = 8/3 d, head dim conventions. | https://www.youtube.com/watch?v=lVynu4bo1rY | 1.5 | Notes | ☐
19 | 2026-10-06 | Tue | W2 | P1 | Reading | Big LLM Architecture Comparison | Read the Llama, Qwen, DeepSeek (MLA/MoE) and gpt-oss sections. | https://magazine.sebastianraschka.com/p/the-big-llm-architecture-comparison | 1 |  | ☐
20 | 2026-10-06 | Tue | W2 | P13 | Paper | Pre-LN, RMSNorm, GLU variants | Short reads: Pre-LN sec. 1+3 (skip proofs), RMSNorm sec. 3, GLU Variants (whole). | https://arxiv.org/abs/2002.04745 | 1 | Paper notes #2 | ☐
21 | 2026-10-07 | Wed | W2 | P1 | Code | Block components | Embeddings + (learned/sinusoidal) PE, LayerNorm & RMSNorm, FFN vs SwiGLU, pre-norm residual block, weight tying. Parameter-count function tested against ~12*L*d^2 + embeddings. | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/01-attention-and-transformer.md | 3.5 | P2: components + tests | ☐
22 | 2026-10-08 | Thu | W2 | P1 | Video | RoPE / GQA explained | Umar Jamil LLaMA explained - RoPE, RMSNorm, GQA, SwiGLU sections. | https://www.youtube.com/watch?v=Mn_9W1nCFLo | 1 |  | ☐
23 | 2026-10-08 | Thu | W2 | P13 | Paper | RoFormer | Sections 3.1-3.4. | https://arxiv.org/abs/2104.09864 | 0.5 |  | ☐
24 | 2026-10-08 | Thu | W2 | P1 | Code | Implement RoPE | Rotation form; test that <RoPE(q,m), RoPE(k,n)> depends only on m-n; compare interleaved (GPT-J) vs half-split (GPT-NeoX/Llama HF) layouts. | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/01-attention-and-transformer.md | 2 | P2: rope.py + test | ☐
25 | 2026-10-09 | Fri | W2 | P13 | Paper | MQA + GQA | MQA sec. 2-3, GQA sec. 2-3. Compute KV-cache bytes for a Llama-3-8B-like config under MHA/GQA/MQA. | https://arxiv.org/abs/2305.13245 | 1 | KV math table | ☐
26 | 2026-10-09 | Fri | W2 | P1 | Code | GQA + assemble GPT | GQA via repeat_interleave; flags for MHA/MQA. Assemble decoder-only GPT (dataclass config). Tests: causal leakage, shapes, param count. | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/01-attention-and-transformer.md | 2.5 | P2: model.py | ☐
27 | 2026-10-10 | Sat | W2 | P1 | Project | Encoder-decoder Transformer | Bidirectional encoder + decoder with cross-attention; train on sequence reversal or 3-digit addition until >99% exact match. | https://nlp.seas.harvard.edu/annotated-transformer/ | 3 | P2: seq2seq.py | ☐
28 | 2026-10-10 | Sat | W2 | P1 | Review | Encoder vs decoder write-up | BERT sec. 3 skim (15 min). Write 1 page: encoder-only vs decoder-only vs enc-dec, and why decoder-only dominates LLMs. | https://arxiv.org/abs/1810.04805 | 1 | P2 README (DONE) | ☐
29 | 2026-10-12 | Mon | W3 | P2 | Video | Let's build the GPT Tokenizer | Watch with minbpe open; pause to implement get_stats/merge yourself. | https://www.youtube.com/watch?v=zduSFxRajkE | 2.5 |  | ☐
30 | 2026-10-12 | Mon | W3 | P13 | Paper | BPE (Sennrich) + GPT-2 input representation | BPE sec. 3.2 + Algorithm 1; GPT-2 sec. 2.2. | https://arxiv.org/abs/1508.07909 | 1 | Paper notes #3 | ☐
31 | 2026-10-13 | Tue | W3 | P2 | Video | CS336 L1 - Overview & tokenization | Video + A1 handout BPE section. | https://www.youtube.com/watch?v=JuoVZkPBiKk | 1.5 |  | ☐
32 | 2026-10-13 | Tue | W3 | P2 | Code | BPE trainer v1 | Naive byte-level BPE trainer with GPT-2 pre-tokenization regex and special tokens. | https://github.com/stanford-cs336/assignment1-basics | 2 | P3: bpe_train.py | ☐
33 | 2026-10-14 | Wed | W3 | P2 | Code | BPE trainer v2 + tokenizer | Incremental pair-count updates, parallel pre-tokenization on chunk boundaries; 10K vocab on TinyStories; encode/decode; run A1 tokenizer tests. | https://github.com/stanford-cs336/assignment1-basics | 2 | P3: tokenizer passes A1 tests | ☐
34 | 2026-10-14 | Wed | W3 | P2 | Experiment | SentencePiece vs BPE | Read SentencePiece sec. 2-3; train BPE vs unigram on same text; compare bytes/token and vocab-size trade-off (embedding params vs sequence length). | https://arxiv.org/abs/1808.06226 | 1.5 | Comparison table | ☐
35 | 2026-10-15 | Thu | W3 | P2 | Reading | LM objective math | Concept note: next-token prediction, cross-entropy = NLL, teacher forcing, perplexity, bits-per-byte. | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/02-prompt-to-next-token.md | 1 |  | ☐
36 | 2026-10-15 | Thu | W3 | P2 | Code | Training loop (A1 components) | memmap token dataset, random batch sampler, own AdamW, warmup + cosine LR, grad clipping, checkpoint save/load; pass the A1 tests for each. | https://github.com/stanford-cs336/assignment1-basics | 2.5 | P3: train.py | ☐
37 | 2026-10-16 | Fri | W3 | P2 | Experiment | Train on TinyStories | ~20-30M params on one rented GPU (or smaller on MPS). Log train/val loss, tokens/s, estimated MFU. Aim for the A1 handout's TinyStories target. | https://github.com/stanford-cs336/assignment1-basics | 3.5 | Loss curves | ☐
38 | 2026-10-17 | Sat | W3 | P2 | Code | Generation + sampling | Temperature, top-k, top-p sampling; generate 20 stories; read them critically. | https://arxiv.org/abs/1904.09751 | 2 | generate.py | ☐
39 | 2026-10-17 | Sat | W3 | P13 | Experiment | Reproduction #1 - architecture ablations | RoPE vs NoPE vs learned absolute; pre-norm vs post-norm at high LR (Pre-LN paper claim); 3-point LR sweep. Plot and explain. | https://arxiv.org/abs/2002.04745 | 2 | Ablation report | ☐
40 | 2026-10-19 | Mon | W4 | P2 | Reading | Prompt -> next token walkthrough | Read the concept note, then step through Bycroft's 3D visualization for one token. | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/02-prompt-to-next-token.md | 1 |  | ☐
41 | 2026-10-19 | Mon | W4 | P2 | Code | KV cache | Pre-allocated K/V tensors per layer, RoPE offsets, prefill vs decode code paths; measure ms/token with vs without cache as T grows. | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/02-prompt-to-next-token.md | 2.5 | P3: kv_cache.py + plot | ☐
42 | 2026-10-20 | Tue | W4 | P13 | Paper | Neural text degeneration | Holtzman et al. sec. 3-5 (why greedy/beam degenerate; nucleus sampling). | https://arxiv.org/abs/1904.09751 | 1 | Paper notes #4 | ☐
43 | 2026-10-20 | Tue | W4 | P2 | Code | Sampling suite | Beam search, top-p, min-p, repetition penalty; experiment distinct-n vs perplexity across settings; sliding-window perplexity eval. | https://arxiv.org/abs/1904.09751 | 2.5 | P3: sampling study | ☐
44 | 2026-10-21 | Wed | W4 | P2 | Video | CS336 L10 - Inference | Trace + video: prefill/decode, arithmetic intensity, KV cache, batching. | https://cs336.stanford.edu/lectures/?trace=lecture_10 | 1.5 |  | ☐
45 | 2026-10-21 | Wed | W4 | P2 | Reading | Transformer inference arithmetic | kipply's post; redo its numbers for a model you care about. | https://kipply.github.io/blog/transformer-inference-arithmetic/ | 1 |  | ☐
46 | 2026-10-21 | Wed | W4 | P2 | Review | Inference math exercises | FLOPs/token ~ 2N; KV bytes/token = 2*L*n_kv*d_head*bytes; decode lower bound = bytes moved / bandwidth. Why long context is expensive (memory + positional extrapolation). | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/02-prompt-to-next-token.md | 1 | inference_math.md | ☐
47 | 2026-10-22 | Thu | W4 | P11 | Reading | Scaling laws | CS336 L9 slides + video; Kaplan sec. 1-3 figures; Chinchilla sec. 3 (IsoFLOP approaches). | https://arxiv.org/abs/2203.15556 | 1.5 | Paper notes #5 | ☐
48 | 2026-10-22 | Thu | W4 | P13 | Experiment | Reproduction #2 - mini IsoFLOP | 3 compute budgets x 4 model sizes on TinyStories (short runs in the background). Fit N_opt vs C and compare the exponent with Chinchilla (~0.5). Use C ~ 6ND. | https://arxiv.org/abs/2203.15556 | 2 | isoflop.ipynb | ☐
49 | 2026-10-23 | Fri | W4 | P1 | Reading | Mixture of Experts | CS336 L4 slides/video + Grootendorst visual guide; Switch sec. 2.1-2.2; Mixtral sec. 2. | https://newsletter.maartengrootendorst.com/p/a-visual-guide-to-mixture-of-experts | 1.5 |  | ☐
50 | 2026-10-23 | Fri | W4 | P1 | Code | MoE layer | Token-choice top-k router, experts as SwiGLU FFNs, load-balancing auxiliary loss; swap into GPT. | https://arxiv.org/abs/2101.03961 | 2 | moe.py | ☐
51 | 2026-10-24 | Sat | W4 | P1 | Experiment | Dense vs MoE | 8 experts top-2 vs dense at matched active params and tokens: loss, tokens/s, expert-utilization histogram. | https://arxiv.org/abs/2101.03961 | 2 | MoE report | ☐
52 | 2026-10-24 | Sat | W4 | P2 | Review | Phase 1-2 checkpoint | Close-book: write 'prompt -> next token' with your own diagram and numbers; answer the Phase 1 and 2 checkpoint questions. | https://github.com/anshu8830/anshu/blob/main/curriculum/08-skill-checkpoints.md | 2 | P3 (DONE) | ☐
53 | 2026-10-26 | Mon | W5 | P3 | Reading | Embeddings + contrastive learning | Concept note; SBERT sec. 3; DPR sec. 3 (in-batch negatives); InfoNCE (CPC sec. 2.3). | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/03-retrieval-and-vector-search.md | 1.5 | Paper notes #6 | ☐
54 | 2026-10-26 | Mon | W5 | P3 | Code | InfoNCE + bi-encoder fine-tune | Implement InfoNCE with temperature; fine-tune all-MiniLM-L6-v2 on QA pairs for 1 epoch; MRR before/after. | https://sbert.net/ | 2 | P4: contrastive.py | ☐
55 | 2026-10-27 | Tue | W5 | P3 | Reading | TF-IDF + BM25 | IR book ch. 6 and sec. 11.4.3. | https://nlp.stanford.edu/IR-book/html/htmledition/irbook.html | 1 |  | ☐
56 | 2026-10-27 | Tue | W5 | P3 | Code | BM25 from scratch | Inverted index, k1/b, IDF variants; compare scores/speed with bm25s on BEIR SciFact. | https://github.com/xhluca/bm25s | 2.5 | P4: bm25.py | ☐
57 | 2026-10-28 | Wed | W5 | P3 | Code | IR metrics | Recall@K, Precision@K, MRR, nDCG@K from scratch with unit tests; BEIR paper sec. 3-5. | https://arxiv.org/abs/2104.08663 | 1 | metrics.py | ☐
58 | 2026-10-28 | Wed | W5 | P13 | Experiment | Reproduction #3 - BEIR baseline | BM25 vs dense (e5/bge-small) vs hybrid RRF on SciFact + NFCorpus; your BM25 nDCG@10 on SciFact should land within ~0.02 of the BEIR table. | https://arxiv.org/abs/2104.08663 | 2.5 | Results table | ☐
59 | 2026-10-29 | Thu | W5 | P3 | Reading | IVF + PQ | Pinecone chapters on vector indexes and PQ; PQ paper sec. II-III. | https://www.pinecone.io/learn/series/faiss/product-quantization/ | 1.5 |  | ☐
60 | 2026-10-29 | Thu | W5 | P3 | Code | IVF-PQ in NumPy | k-means coarse quantizer + nprobe; PQ with m sub-spaces x 256 centroids; ADC tables; recall@10 vs nprobe and bytes/vector. | https://doi.org/10.1109/TPAMI.2010.57 | 2 | P4: ivfpq.py | ☐
61 | 2026-10-30 | Fri | W5 | P3 | Video | HNSW | James Briggs video, then HNSW paper sec. 3-4 (Algorithms 1-4). | https://www.youtube.com/watch?v=QvKMwLjdK-s | 1.5 |  | ☐
62 | 2026-10-30 | Fri | W5 | P3 | Code | NSW/HNSW | Single-layer NSW with beam search (efSearch), then hierarchy (optional); compare with FAISS IndexHNSWFlat over M/efSearch. | https://arxiv.org/abs/1603.09320 | 2 | P4: hnsw.py + curves | ☐
63 | 2026-10-31 | Sat | W5 | P3 | Project | Assemble retrieval engine | One interface over BM25, Flat, IVF-PQ, HNSW (yours + FAISS), hybrid RRF, cross-encoder reranker, metadata filters, and one DB backend (pgvector HNSW or Qdrant). | https://www.pinecone.io/learn/series/faiss/ | 3 | P4 package | ☐
64 | 2026-10-31 | Sat | W5 | P3 | Review | Benchmark report | Recall/nDCG/latency/memory table across indexes; notes on pre- vs post-filtering in vector DBs. | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/03-retrieval-and-vector-search.md | 1 | P4 (DONE) | ☐
65 | 2026-11-02 | Mon | W6 | P4 | Video | RAG foundations | RAG paper sec. 2 (RAG-Sequence vs RAG-Token) + Kiela CS25 lecture. | https://www.youtube.com/watch?v=mE7IDf2SmJg | 1.5 | Paper notes #7 | ☐
66 | 2026-11-02 | Mon | W6 | P4 | Code | Baseline pipeline + golden set v0 | Docling parse -> fixed chunks -> embed -> retrieve (P4) -> numbered sources -> answer with citations. Write 30 real Q/A pairs now. | https://docling-project.github.io/docling/ | 2 | P5 baseline | ☐
67 | 2026-11-03 | Tue | W6 | P4 | Video | Advanced retrieval practice | Clavie talk + Anthropic Contextual Retrieval. | https://www.youtube.com/watch?v=0nA5QG3087g | 1 |  | ☐
68 | 2026-11-03 | Tue | W6 | P4 | Experiment | Chunking study | Fixed vs recursive vs structure-aware vs semantic; parent-child; contextual headers; metadata filters. Measure recall@5 on golden set. | https://www.anthropic.com/news/contextual-retrieval | 2.5 | Chunking table | ☐
69 | 2026-11-04 | Wed | W6 | P13 | Paper | HyDE + query-side methods | HyDE sec. 3; multi-query, decomposition, conversational rewriting. | https://arxiv.org/abs/2212.10496 | 1 |  | ☐
70 | 2026-11-04 | Wed | W6 | P4 | Code | Full retrieval chain | Rewrite -> multi-query -> hybrid -> RRF -> cross-encoder rerank -> extractive compression -> generate; ablate each stage. | https://arxiv.org/abs/2212.10496 | 2.5 | P5 chain | ☐
71 | 2026-11-05 | Thu | W6 | P4 | Paper | Lost in the Middle | Sec. 2-4; implement context ordering (best chunks at edges) and token budgets. | https://arxiv.org/abs/2307.03172 | 1 |  | ☐
72 | 2026-11-05 | Thu | W6 | P4 | Paper | Late interaction | ColBERT sec. 3 (MaxSim); BGE-M3 dense+sparse+multi-vector. | https://arxiv.org/abs/2004.12832 | 1 |  | ☐
73 | 2026-11-05 | Thu | W6 | P4 | Code | Multi-vector path | BGE-M3 multi-vector or ColBERT-style MaxSim reranker vs cross-encoder: quality vs latency. | https://arxiv.org/abs/2402.03216 | 1.5 |  | ☐
74 | 2026-11-06 | Fri | W6 | P4 | Paper | Agentic & graph RAG | Self-RAG overview; GraphRAG sec. 2-3; retrieval planning (whether / what / how many hops). | https://arxiv.org/abs/2404.16130 | 1.5 |  | ☐
75 | 2026-11-06 | Fri | W6 | P4 | Code | Agentic RAG router | Answer-directly / retrieve / decompose router, sufficiency check, max hops; optional entity graph for global questions. | https://arxiv.org/abs/2310.11511 | 2 | router.py | ☐
76 | 2026-11-07 | Sat | W6 | P4 | Project | P5 polish | Config-driven pipeline, span-level citations, abstain when unsupported, caching, streaming FastAPI endpoint. | https://arxiv.org/abs/2005.11401 | 2.5 | P5 service | ☐
77 | 2026-11-07 | Sat | W6 | P4 | Reading | Map P5 onto LangChain + LlamaIndex | Read-only: how LangChain (document loaders, text splitters, retrievers, vector-store integrations) and LlamaIndex (nodes, indices, query engines, rerankers) name the stages you just built. You should recognise every abstraction as something you already wrote. | https://developers.llamaindex.ai/python/framework/ | 0.5 | mapping table | ☐
78 | 2026-11-07 | Sat | W6 | P4 | Review | Ablation table v0 | Retrieval recall@5 + manual answer check per configuration (full metrics next week). | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/04-rag-and-evaluation-metrics.md | 1 | P5 (DONE) | ☐
79 | 2026-11-09 | Mon | W7 | P5 | Reading | Evals mindset | Husain 'Your AI Product Needs Evals' + first half of the judge guide. | https://hamel.dev/blog/posts/evals/ | 1.5 |  | ☐
80 | 2026-11-09 | Mon | W7 | P5 | Experiment | Error analysis + golden set v1 | Read 50 P5 traces, open-code failures into a taxonomy; grow the golden set to 100+ (human-written, synthetic-then-verified, unanswerable/adversarial). | https://hamel.dev/blog/posts/evals/ | 2 | taxonomy.md + dataset | ☐
81 | 2026-11-10 | Tue | W7 | P13 | Paper | LLM-as-judge research | MT-Bench sec. 3-4 (biases), G-Eval sec. 2, Yan's survey, Shankar 'Who Validates the Validators'. | https://arxiv.org/abs/2306.05685 | 1.5 | Paper notes #8 | ☐
82 | 2026-11-10 | Tue | W7 | P5 | Code | Judges + calibration | Binary rubric judge, pairwise with position swap, reference-based correctness. Label 60 examples yourself; iterate until judge-human kappa >= 0.6. | https://hamel.dev/blog/posts/llm-judge/ | 2 | judges.py + calibration | ☐
83 | 2026-11-11 | Wed | W7 | P5 | Reading | RAG metric definitions | RAGAS sec. 3 + concept note. | https://arxiv.org/abs/2309.15217 | 1 |  | ☐
84 | 2026-11-11 | Wed | W7 | P5 | Code | RAG metrics from scratch | Context precision/recall (gold passages), faithfulness (claim extraction -> per-claim support check), answer relevance, citation accuracy; compare with the ragas library. | https://docs.ragas.io/en/stable/concepts/metrics/available_metrics/ | 2.5 | rag_metrics.py | ☐
85 | 2026-11-12 | Thu | W7 | P5 | Video | Benchmarks & contamination | CS336 L12 trace/video; skim the HF Evaluation Guidebook. | https://cs336.stanford.edu/lectures/?trace=lecture_12 | 1 |  | ☐
86 | 2026-11-12 | Thu | W7 | P5 | Reading | Statistics for evals | Bootstrap CIs, paired tests (paired bootstrap / McNemar), sample sizes; online A/B tests (unit of randomization, guardrails); human-eval protocols and inter-annotator agreement. | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/04-rag-and-evaluation-metrics.md | 1 | stats.py | ☐
87 | 2026-11-12 | Thu | W7 | P5 | Code | Standard benchmark harnesses | Run lm-evaluation-harness on a small open model (ARC-easy, HellaSwag, GSM8K subset); write one custom Inspect task. | https://inspect.aisi.org.uk/ | 1.5 |  | ☐
88 | 2026-11-13 | Fri | W7 | P5 | Reading | Agent & tool-call evals | Anthropic agent-evals post; tau-bench sec. 3-4 (pass^k, DB-state checks); tool-selection accuracy, argument AST match, trajectory efficiency. | https://www.anthropic.com/engineering/demystifying-evals-for-ai-agents | 1.5 |  | ☐
89 | 2026-11-13 | Fri | W7 | P5 | Code | Agent eval schema | Task format, outcome graders (tests pass / state), trajectory graders, cost/latency; write 20 tasks for P8 and the capstone. | https://arxiv.org/abs/2406.12045 | 2 | agent_tasks.jsonl | ☐
90 | 2026-11-14 | Sat | W7 | P5 | Project | Build ragevals | Runners, metrics, calibration report, bootstrap CIs, pytest + GitHub Actions gate that fails on a significant regression, markdown/HTML report. | https://hamel.dev/blog/posts/llm-judge/ | 3 | P6 package | ☐
91 | 2026-11-14 | Sat | W7 | P5 | Review | Re-score P5 ablations | Publish the ablation table with CIs and pick the production config. | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/04-rag-and-evaluation-metrics.md | 1 | P6 (DONE) | ☐
92 | 2026-11-16 | Mon | W8 | P6 | Video | Post-training landscape | CS336 L15 slides + video; InstructGPT sec. 3.1-3.5; pretraining vs continued pretraining vs instruction tuning. | https://github.com/stanford-cs336/lectures/blob/main/lecture_15.pdf | 1.5 | Paper notes #9 | ☐
93 | 2026-11-16 | Mon | W8 | P6 | Reading | Chat templates | HF LLM course ch. 11 + chat templating docs; inspect the Jinja template of Qwen3 or Llama-3 and its special tokens. | https://huggingface.co/docs/transformers/chat_templating | 2 |  | ☐
94 | 2026-11-17 | Tue | W8 | P6 | Code | SFT from scratch | SmolLM2-360M or Qwen3-0.6B-Base: chat template, assistant-only masking with -100, packing caveats, eval loss; then replicate with TRL SFTTrainer and compare loss curves. | https://huggingface.co/docs/trl/sft_trainer | 3.5 | P7: sft.py | ☐
95 | 2026-11-18 | Wed | W8 | P6 | Paper | LoRA | LoRA sec. 4 + 'LoRA Without Regret'. | https://arxiv.org/abs/2106.09685 | 1 |  | ☐
96 | 2026-11-18 | Wed | W8 | P6 | Code | LoRA from scratch | LoRALinear (freeze base, A random, B=0, alpha/r, dropout, merge/unmerge); inject into q,k,v,o + MLP; verify trainable params; compare with PEFT. | https://thinkingmachines.ai/blog/lora/ | 2.5 | P7: lora.py | ☐
97 | 2026-11-19 | Thu | W8 | P6 | Paper | QLoRA + quantization basics | QLoRA sec. 3; first half of the quantization visual guide (absmax, zero-point, block-wise). | https://arxiv.org/abs/2305.14314 | 1 |  | ☐
98 | 2026-11-19 | Thu | W8 | P6 | Experiment | QLoRA an 8B model | Qwen3-8B or Llama-3.1-8B on one 24 GB GPU via Unsloth (or TRL+PEFT+bitsandbytes). Track VRAM and tokens/s; save adapter; merge for serving. | https://unsloth.ai/docs/get-started/fine-tuning-llms-guide | 2.5 | Adapter | ☐
99 | 2026-11-20 | Fri | W8 | P6 | Reading | Dataset preparation | Task spec, sourcing, synthetic generation with verification, dedup, decontamination vs eval set, chat formatting, splits (smol-course modules). | https://github.com/huggingface/smol-course | 1.5 |  | ☐
100 | 2026-11-20 | Fri | W8 | P6 | Code | Build the P7 dataset | 2-5K examples for your capstone task (e.g. JSON tool calls for your own MCP tools) + held-out eval set. | https://github.com/huggingface/smol-course | 2 | dataset v1 | ☐
101 | 2026-11-21 | Sat | W8 | P13 | Experiment | P7 runs + Reproduction #4 | Baseline vs LoRA r in {8, 64} vs QLoRA; LR sweep to test the ~10x-higher optimal LoRA LR finding; eval with P6 harness + tool-call exact match; forgetting check. | https://thinkingmachines.ai/blog/lora/ | 3 | Runs | ☐
102 | 2026-11-21 | Sat | W8 | P6 | Review | Report + publish adapter | Write the report; push the adapter to the HF Hub (private). | https://arxiv.org/abs/2106.09685 | 1 | P7 part 1 (DONE) | ☐
103 | 2026-11-23 | Mon | W9 | P12 | Reading | RL essentials | Spinning Up Part 1 (key concepts) and Part 3 (policy optimization); Abbeel L3. | https://spinningup.openai.com/en/latest/spinningup/rl_intro3.html | 1.5 |  | ☐
104 | 2026-11-23 | Mon | W9 | P12 | Code | REINFORCE on a toy LM | Train your W3 GPT (or a tiny model) to maximize a verifiable reward; compare variance with/without baseline. | https://www.youtube.com/watch?v=AKbX1Zvo7r8 | 2 | reinforce.py | ☐
105 | 2026-11-24 | Tue | W9 | P12 | Paper | PPO + RLHF | PPO sec. 3-5; Christiano 2017 method; InstructGPT RM/PPO sections; RLHF book reward-model + policy-gradient chapters. | https://arxiv.org/abs/1707.06347 | 1.5 | Paper notes #10 | ☐
106 | 2026-11-24 | Tue | W9 | P12 | Video | RLHF with code | Umar Jamil RLHF video - PPO + RLHF sections. | https://www.youtube.com/watch?v=qGyFrqc34yc | 1 |  | ☐
107 | 2026-11-24 | Tue | W9 | P12 | Code | Reward model | Bradley-Terry loss + scalar head on your SFT model; train on ~2K preference pairs; report pairwise accuracy. | https://rlhfbook.com/ | 1 | rm.py | ☐
108 | 2026-11-25 | Wed | W9 | P6 | Paper | DPO derivation | DPO sec. 4-5 + Appendix A.1, with Umar Jamil's DPO video. | https://www.youtube.com/watch?v=hvGa5Mba4c8 | 1 |  | ☐
109 | 2026-11-25 | Wed | W9 | P6 | Code | DPO from scratch | Policy/reference log-probs of chosen vs rejected, beta; train on your P7 SFT model with a preference subset; compare with TRL DPOTrainer; skim ORPO/KTO/SimPO differences. | https://arxiv.org/abs/2305.18290 | 2.5 | P7: dpo.py | ☐
110 | 2026-11-26 | Thu | W9 | P12 | Paper | Reasoning models + RLVR | DeepSeekMath sec. 4 (GRPO), DeepSeek-R1 sec. 2-3, Tulu 3 RLVR section, CS336 L16; skim 'Why We Think'. | https://arxiv.org/abs/2402.03300 | 2 | Paper notes #11 | ☐
111 | 2026-11-26 | Thu | W9 | P12 | Reading | Reward hacking + verifiers | Weng's reward-hacking post; design format + answer verifiers and tests that try to hack them. | https://lilianweng.github.io/posts/2024-11-28-reward-hacking/ | 1.5 | verifiers.py | ☐
112 | 2026-11-27 | Fri | W9 | P12 | Paper | Dr. GRPO + DAPO | Dr. GRPO sec. 2-3 (length bias), DAPO sec. 3 (clip-higher, dynamic sampling, token-level loss, overlong shaping); HF course ch. 12. | https://arxiv.org/abs/2503.20783 | 1 |  | ☐
113 | 2026-11-27 | Fri | W9 | P12 | Code | GRPO from scratch | Group sampling, normalized advantages, clipped ratio, KL to reference, token-level averaging; unit-test on synthetic logits; rollouts via HF generate or vLLM. | https://huggingface.co/learn/llm-course/en/chapter12/4 | 2.5 | P7: grpo.py | ☐
114 | 2026-11-28 | Sat | W9 | P13 | Experiment | GRPO run + Reproduction #5 | Qwen3-0.6B (or Qwen2.5-0.5B/1.5B-Instruct) on GSM8K-style math, 1 rented GPU for 3-4 h (your loop or TRL GRPOTrainer). Track reward, length, held-out accuracy; compare length growth with/without Dr. GRPO normalization. | https://arxiv.org/abs/2503.20783 | 3 | GRPO curves | ☐
115 | 2026-11-28 | Sat | W9 | P12 | Review | Connect to reasoning models | Write-up: RLVR, test-time compute, s1 budget forcing (s1 sec. 2-3), and the reward hacks you observed. | https://arxiv.org/abs/2501.19393 | 1 | P7 (DONE) | ☐
116 | 2026-11-30 | Mon | W10 | P7 | Reading | Agent design principles | Anthropic 'Building effective agents' + Barry Zhang talk; ReAct sec. 2-3. | https://www.anthropic.com/engineering/building-effective-agents | 1 | Paper notes #12 | ☐
117 | 2026-11-30 | Mon | W10 | P7 | Code | Raw agent loop | No framework. JSON-schema tools (search via P5, sandboxed python exec, file read), parse tool calls, execute, append results, max-steps, retries, token/cost accounting, trajectory logs. | https://arxiv.org/abs/2210.03629 | 2.5 | P8: loop.py | ☐
118 | 2026-12-01 | Tue | W10 | P7 | Reading | Planning, reflection, memory | Weng agents post; Reflexion sec. 3; MemGPT sec. 2-3; Anthropic context-engineering post. | https://www.anthropic.com/engineering/effective-context-engineering-for-ai-agents | 1.5 |  | ☐
119 | 2026-12-01 | Tue | W10 | P7 | Code | Plan/reflect/remember | Plan-and-execute mode, verifier-driven self-critique, context compaction, episodic + semantic long-term memory in a vector store, typed state persisted to Postgres/SQLite. | https://arxiv.org/abs/2310.08560 | 2 | P8: memory.py | ☐
120 | 2026-12-02 | Wed | W10 | P7 | Reading | Tools, security, multi-agent | Anthropic tool-writing post; OWASP LLM Top 10; lethal trifecta; Anthropic multi-agent research system. | https://www.anthropic.com/engineering/writing-tools-for-agents | 1.5 |  | ☐
121 | 2026-12-02 | Wed | W10 | P7 | Code | HITL + security + multi-agent | Approval gates for side-effecting tools, allow-lists, sandbox, injection tests (poisoned document in the RAG corpus); orchestrator + 2 sub-agents. | https://simonwillison.net/2025/Jun/16/the-lethal-trifecta/ | 2 | security tests | ☐
122 | 2026-12-03 | Thu | W10 | P8 | Reading | MCP spec | 2026-07-28 spec (architecture, tools/resources/prompts, transports, authorization) + release notes; HF MCP course unit 1. Note: many tutorials still show the older stateful 2025 revisions. | https://modelcontextprotocol.io/specification/2026-07-28 | 1.5 |  | ☐
123 | 2026-12-03 | Thu | W10 | P8 | Code | Project 9 - MCP server | Python SDK server over your retrieval engine: tools (search, fetch_doc), resources (doc://{id}), prompts (cite-answer); stdio + Streamable HTTP; test with MCP Inspector; call it from your agent. | https://huggingface.co/learn/mcp-course/en/unit0/introduction | 2 | P9 server | ☐
124 | 2026-12-04 | Fri | W10 | P7 | Code | LangChain 1.0 agents | Chat models + messages, @tool, structured output, create_agent, middleware (human-in-the-loop, summarization). Rebuild your raw loop with create_agent and map every piece; note that create_agent returns a compiled LangGraph graph. | https://docs.langchain.com/oss/python/langchain/middleware/overview | 1 | langchain_agent.py | ☐
125 | 2026-12-04 | Fri | W10 | P7 | Code | LangGraph core | StateGraph, typed state + reducers, conditional edges, checkpointer (persistence, time travel), interrupt() for approval, streaming. LangChain Academy 'Intro to LangGraph' modules 1-3 (selected lessons) as you code. | https://academy.langchain.com/courses/intro-to-langgraph | 1.5 | langgraph_agent.py | ☐
126 | 2026-12-04 | Fri | W10 | P7 | Reading | Other frameworks | Tiny example each: smolagents CodeAgent, OpenAI Agents SDK (handoffs, guardrails, sessions), LlamaIndex Workflows. Write a 1-page comparison including LangChain/LangGraph. | https://openai.github.io/openai-agents-python/ | 1 | frameworks.md | ☐
127 | 2026-12-05 | Sat | W10 | P7 | Project | Project 8 - research agent on LangGraph | Production version built on LangGraph (your raw loop stays as the reference): question -> plan -> search (arXiv API + your RAG via MCP) -> read -> synthesize with citations -> self-critique -> revise; interrupt() before final; traces in LangSmith or your own tracer. Compare traces with the raw loop. | https://docs.langchain.com/oss/python/langgraph/overview | 3 | P8 agent | ☐
128 | 2026-12-05 | Sat | W10 | P7 | Review | Evaluate agent + harden MCP | Run the 20 W7 tasks: citation faithfulness, success, steps, cost. Add auth to the HTTP transport per the spec. | https://www.anthropic.com/engineering/demystifying-evals-for-ai-agents | 1 | P8 + P9 (DONE) | ☐
129 | 2026-12-07 | Mon | W11 | P9 | Reading | GPU architecture | GPU Glossary (SM, warp, tensor core, HBM, L2, shared memory, occupancy); CS336 L5 slides + video. | https://modal.com/gpu-glossary | 1.5 |  | ☐
130 | 2026-12-07 | Mon | W11 | P9 | Reading | Compute vs memory vs overhead | Horace He 'brrr'. | https://horace.io/brrr_intro.html | 1 |  | ☐
131 | 2026-12-07 | Mon | W11 | P9 | Review | Roofline exercises | Scaling-book roofline chapter; intensity of (B,d)x(d,d) in bf16; H100 ridge point; decode-bound analysis. | https://jax-ml.github.io/scaling-book/roofline/ | 1 | roofline.py | ☐
132 | 2026-12-08 | Tue | W11 | P9 | Video | Kernels & Triton | CS336 L6 trace + video; CUDA model (grid/block/thread, coalescing) from the glossary. | https://cs336.stanford.edu/lectures/?trace=lecture_06 | 1.5 |  | ☐
133 | 2026-12-08 | Tue | W11 | P9 | Code | Profile + first kernels | torch.profiler on your GPT (top kernels, memory-bound ops), torch.compile speedup; write Triton vector-add and fused softmax and benchmark vs PyTorch. | https://triton-lang.org/main/getting-started/tutorials/02-fused-softmax.html | 2 | kernels/ | ☐
134 | 2026-12-09 | Wed | W11 | P13 | Paper | FlashAttention | Sec. 2-3 (tiling, online softmax, recomputation, IO complexity) + Tri Dao talk; FA2 abstract. | https://arxiv.org/abs/2205.14135 | 1.5 | Paper notes #13 | ☐
135 | 2026-12-09 | Wed | W11 | P9 | Code | Online-softmax tiled attention | Block loops in PyTorch; verify equality with naive attention; count HBM reads/writes analytically. | https://www.youtube.com/watch?v=gMOAud7hZg4 | 2 | flash_ref.py | ☐
136 | 2026-12-10 | Thu | W11 | P9 | Reading | Serving systems | vLLM paper sec. 3-4; Gordic 'Inside vLLM'; Sarathi-Serve abstract + sec. 3; TTFT, TPOT/ITL, throughput, goodput. | https://www.aleksagordic.com/blog/vllm | 1.5 |  | ☐
137 | 2026-12-10 | Thu | W11 | P9 | Reading | Quantization for inference | FP32/FP16/BF16/FP8/INT8/INT4 layouts; LLM.int8 outliers; GPTQ and AWQ core ideas; KV-cache quantization; second half of the visual guide. | https://newsletter.maartengrootendorst.com/p/a-visual-guide-to-quantization | 2 | quant notes | ☐
138 | 2026-12-11 | Fri | W11 | P9 | Paper | Speculative decoding | Leviathan et al. sec. 2-3 + Efficient NLP video. | https://arxiv.org/abs/2211.17192 | 1 |  | ☐
139 | 2026-12-11 | Fri | W11 | P9 | Code | Speculative sampling | Draft = tiny GPT, target = larger GPT; acceptance rate and speedup vs k. | https://www.youtube.com/watch?v=S-8yr_RibJ4 | 1.5 | specdec.py | ☐
140 | 2026-12-11 | Fri | W11 | P9 | Reading | TensorRT-LLM overview | Engine building, in-flight batching, FP8/FP4; compare with vLLM (read-only). | https://nvidia.github.io/TensorRT-LLM/ | 1 |  | ☐
141 | 2026-12-12 | Sat | W11 | P9 | Project | Project 10 - vLLM serving | Serve Qwen3-8B (and/or your merged P7 model) on a rented GPU; load test at concurrency 1/8/32/128; BF16 vs FP8 vs AWQ-INT4; prefix caching on/off; speculative decoding on/off. | https://github.com/vllm-project/vllm | 3 | Benchmarks | ☐
142 | 2026-12-12 | Sat | W11 | P13 | Review | Perf report + Reproduction #6 | Explain every number with roofline/memory math; continuous vs static batching throughput. | https://arxiv.org/abs/2309.06180 | 1 | P10 (DONE) | ☐
143 | 2026-12-14 | Mon | W12 | P11 | Reading | Memory + data parallelism | Ultra-Scale Playbook: memory anatomy, activation recomputation, gradient accumulation, DP, ZeRO-1/2/3; ZeRO sec. 5; mixed precision. | https://huggingface.co/spaces/nanotron/ultrascale-playbook | 2 | Paper notes #14 | ☐
144 | 2026-12-14 | Mon | W12 | P11 | Code | Memory calculator | 8B full fine-tune under DDP vs ZeRO-3 on 8x80GB incl. activations and checkpointing; optional DDP/FSDP run of your GPT on 2 GPUs. | https://arxiv.org/abs/1910.02054 | 1.5 | mem_calc.py | ☐
145 | 2026-12-15 | Tue | W12 | P11 | Reading | Model parallelism | Playbook TP (column/row), sequence/context parallel, PP (GPipe, 1F1B); Megatron sec. 3; CS336 L7-8; read picotron tensor_parallel.py. | https://github.com/huggingface/picotron | 2 |  | ☐
146 | 2026-12-15 | Tue | W12 | P11 | Reading | Pretraining data | CS336 L13-14 (sources, filtering, dedup, mixing, synthetic) + FineWeb sec. 3-4. Exercise: layout for 70B on 64xH100 + a data-pipeline sketch. | https://arxiv.org/abs/2406.17557 | 1.5 | design.md | ☐
147 | 2026-12-16 | Wed | W12 | P10 | Paper | ViT + CLIP | ViT sec. 3.1 (patches as tokens; CNN revision: patch embed = strided conv); CLIP sec. 2 + Figure 3; SigLIP abstract. | https://arxiv.org/abs/2103.00020 | 1.5 | Paper notes #15 | ☐
148 | 2026-12-16 | Wed | W12 | P10 | Code | CLIP from the loss up | Symmetric InfoNCE + patch embedding; zero-shot classification and text-image retrieval with OpenCLIP. | https://huggingface.co/learn/computer-vision-course/en/unit4/multimodal-models/clip-and-relatives/clip | 2 | clip.ipynb | ☐
149 | 2026-12-17 | Thu | W12 | P10 | Reading | VLM architecture | Raschka multimodal article; LLaVA sec. 3-4 (projector, 2-stage training); HF VLMs 2025; Umar Jamil PaliGemma sections. | https://magazine.sebastianraschka.com/p/understanding-multimodal-llms | 1.5 |  | ☐
150 | 2026-12-17 | Thu | W12 | P10 | Code | nanoVLM | Read vision encoder -> modality projector -> LM; run a short training (or fine-tune SmolVLM with TRL); inspect how image tokens enter the sequence. | https://github.com/huggingface/nanoVLM | 2 | vlm notes | ☐
151 | 2026-12-18 | Fri | W12 | P10 | Paper | Documents, audio, video | ColPali sec. 3-4 + blog; OCR (Docling) vs OCR-free; tables/charts; Whisper sec. 2 + run it; TTS overview; video = frame sampling + VLM. | https://arxiv.org/abs/2407.01449 | 1.5 |  | ☐
152 | 2026-12-18 | Fri | W12 | P10 | Code | Multimodal ingestion | PDF -> Docling text/tables + page images -> ColPali/ColQwen embeddings; audio -> Whisper transcripts with timestamps. | https://github.com/illuin-tech/colpali | 2 | ingest.py | ☐
153 | 2026-12-19 | Sat | W12 | P10 | Project | Project 11 - multimodal RAG | Hybrid text + page-image retrieval; VLM answers over retrieved pages with page citations; voice queries via Whisper. | https://github.com/illuin-tech/colpali | 3 | P11 app | ☐
154 | 2026-12-19 | Sat | W12 | P10 | Review | Evaluate | 50 multimodal questions (charts, tables, scanned pages) through ragevals; text-only vs image retrieval. | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/04-rag-and-evaluation-metrics.md | 1 | P11 (DONE) | ☐
155 | 2026-12-21 | Mon | W13 | CAP | Review | Design review | Re-read the capstone spec, threat model and eval plan; read mini-swe-agent end to end. | https://github.com/SWE-agent/mini-swe-agent | 1 | ADR.md | ☐
156 | 2026-12-21 | Mon | W13 | CAP | Project | M1 - repo understanding | tree-sitter parsing, symbol graph + ranked repo map, function/class-level chunking, hybrid code search via P4; expose as a 'repo-intel' MCP server. | https://aider.chat/docs/repomap.html | 2.5 | M1 | ☐
157 | 2026-12-22 | Tue | W13 | CAP | Project | M2 - agent core | Planner -> executor loop from P8 with read_file, search_code, edit_file (patch), run_tests, run_shell (Docker, no network), git_diff; task scratchpad + long-term repo notes. | https://github.com/SWE-agent/mini-swe-agent | 3.5 | M2 | ☐
158 | 2026-12-23 | Wed | W13 | CAP | Project | M3 - execution, testing, routing, HITL | Reproduce the bug with a failing test first; edit-test loop with budget; approval before applying patches; router: small vLLM model for cheap steps, frontier model for planning/editing, with fallback. | https://arxiv.org/abs/2406.18665 | 3.5 | M3 | ☐
159 | 2026-12-24 | Thu | W13 | CAP | Project | M4 - multimodal + MCP + observability | Screenshot/diagram of a bug -> VLM description; docs RAG (P5); MCP client to your servers (P9 + repo-intel); per-step tracing. | https://huggingface.co/blog/vlms-2025 | 3.5 | M4 | ☐
160 | 2026-12-25 | Fri | W13 | CAP | Buffer | Rest / buffer (25 Dec) | Holiday. Use only to catch up if you are behind. |  | 0 |  | ☐
161 | 2026-12-26 | Sat | W13 | CAP | Project | M5 - evaluation | 30 in-house tasks (bug fix, add test, refactor) + 20-50 SWE-bench Lite/Verified instances via the official harness: resolve rate, cost, steps, approval rate. | https://github.com/SWE-bench/SWE-bench | 4 | M5 results | ☐
162 | 2026-12-28 | Mon | W14 | CAP | Project | M6 - error analysis + ablations | Fix the top failure modes; ablate repo map, routing, reflection. | https://www.anthropic.com/engineering/demystifying-evals-for-ai-agents | 3.5 | M6 | ☐
163 | 2026-12-29 | Tue | W14 | CAP | Project | M7 - hardening | Prompt-injection tests (malicious README/issue text), secret redaction, cost/time budgets; eval regression suite in CI via ragevals. | https://genai.owasp.org/llm-top-10/ | 3.5 | M7 | ☐
164 | 2026-12-30 | Wed | W14 | CAP | Project | M8 - demo + write-up | Architecture, results table, lessons learned, recorded demo. | https://github.com/anshu8830/anshu/blob/main/curriculum/09-capstone-ai-software-engineer.md | 2 | Capstone (DONE) | ☐
165 | 2026-12-30 | Wed | W14 | P13 | Review | Final close-book assessment | All phase checkpoints; update the skills sheet honestly. | https://github.com/anshu8830/anshu/blob/main/curriculum/08-skill-checkpoints.md | 1.5 | Assessment | ☐
166 | 2026-12-31 | Thu | W14 | P13 | Review | Retrospective + 2027 plan | Pick a 2027 track; schedule the deferred items into Q1. | https://github.com/anshu8830/anshu/blob/main/curriculum/10-2027-continuation.md | 2 | 2027 plan | ☐
167 | 2026-12-31 | Thu | W14 | P13 | Review | Publish portfolio | Clean READMEs for the 11 projects + capstone; a 'what I built in 13 weeks' post. | https://github.com/anshu8830/anshu/blob/main/curriculum/09-capstone-ai-software-engineer.md | 1.5 | Portfolio | ☐

## Projects
ID | Project | Weeks | Due | Deliverable | Skills developed | Status | Done | Your repo link / notes
P1 | Attention from scratch | W1 | 2026-10-03 | attention.py (SDPA, masks, MHA, cross-attn) + pytest suite + experiment notebook | Q/K/V shapes, masking, sqrt(d_k) scaling, tests against PyTorch reference | Not started | ☐
P2 | Transformer from scratch | W2 | 2026-10-10 | Decoder-only GPT (RoPE, RMSNorm, SwiGLU, GQA) + encoder-decoder trained on a toy seq2seq task | Block design, pre-norm residuals, RoPE, GQA, param counting | Not started | ☐
P3 | Tokenizer + small GPT trained end-to-end | W3-W4 | 2026-10-24 | Byte-level BPE, training loop, TinyStories model, KV-cache generation, sampling suite, ablation report | BPE, cross-entropy/perplexity, AdamW + schedules, KV cache, sampling, scaling-law fit, MoE layer | Not started | ☐
P4 | Embedding & retrieval engine | W5 | 2026-10-31 | BM25, IVF-PQ, HNSW (own + FAISS), hybrid RRF, reranker, pgvector/Qdrant backend, benchmark report | Contrastive learning, sparse vs dense retrieval, ANN algorithms, IR metrics | Not started | ☐
P5 | Advanced RAG system | W6 | 2026-11-07 | Config-driven RAG: parsing, chunking variants, query rewriting/HyDE, hybrid+rerank, agentic router, citations | Every RAG stage + its failure modes, ablation discipline | Not started | ☐
P6 | RAG / LLM evaluation framework | W7 | 2026-11-14 | ragevals: golden sets, retrieval + judge metrics, judge calibration, bootstrap CIs, CI regression gate | Error analysis, LLM-as-judge, faithfulness, statistics, regression testing | Not started | ☐
P7 | Fine-tune an open LLM (SFT + LoRA/QLoRA + DPO + GRPO) | W8-W9 | 2026-11-28 | SFT-from-scratch, LoRA-from-scratch, QLoRA 8B run, DPO run, GRPO run on verifiable math, eval report | Chat templates, loss masking, LoRA/QLoRA, preference optimization, RLVR | Not started | ☐
P8 | AI research agent | W10 | 2026-12-05 | Framework-free agent loop -> planning, memory, reflection, HITL; LangGraph port; agent eval on 20 tasks | Tool calling, ReAct, memory, multi-agent, agent security, agent evaluation | Not started | ☐
P9 | Custom MCP server | W10 | 2026-12-05 | MCP server over your retrieval engine: tools + resources + prompts, stdio + Streamable HTTP, auth, tests | MCP architecture, transports, auth, tool design | Not started | ☐
P10 | Optimize & serve an LLM with vLLM | W11 | 2026-12-12 | Benchmarked vLLM deployment: BF16/FP8/INT4, prefix caching, spec decoding; perf report with roofline math | GPU fundamentals, KV cache, batching, quantization, TTFT/TPOT | Not started | ☐
P11 | Multimodal RAG | W12 | 2026-12-19 | PDF/figure/table/audio RAG: Docling + ColPali-style page retrieval + VLM answers with page citations | ViT/CLIP, VLM architecture, document understanding, Whisper | Not started | ☐
CAP | Capstone: AI Software Engineer | W13-W14 | 2026-12-31 | Repo-aware coding agent with RAG, MCP, memory, planning, sandboxed execution, routing, HITL, eval on SWE-bench subset | Everything - integration, evaluation and hardening | Not started | ☐

## Papers
# | Title | Authors | Year | Difficulty (1-5) | Week | Link | Why it matters | Prerequisites | Read carefully | Implement | Reproduce | Tier | Read | Notes
1 | How to Read a Paper | S. Keshav | 2007 | 1 | W1 | http://ccr.sigcomm.org/online/files/p83-keshavA.pdf | The three-pass method you will use for every paper below. | None. | Whole paper (2 pages). | A paper-notes template in your repo. | - | CORE | ☐
2 | Improving Language Understanding by Generative Pre-Training (GPT-1) | Radford, Narasimhan, Salimans, Sutskever | 2018 | 1 | W2 | https://cdn.openai.com/research-covers/language-unsupervised/language_understanding_paper.pdf | Origin of generative pretraining + fine-tuning. | Attention Is All You Need. | Sections 1, 3.1-3.3. | - | - | CORE | ☐
3 | GLU Variants Improve Transformer | Shazeer | 2020 | 1 | W2 | https://arxiv.org/abs/2002.05202 | Source of SwiGLU used in Llama/Qwen. | FFN block; gating. | Whole paper (4 pages). | SwiGLU FFN. | - | CORE | ☐
4 | Neural Machine Translation of Rare Words with Subword Units (BPE) | Sennrich, Haddow, Birch | 2015 | 1 | W3 | https://arxiv.org/abs/1508.07909 | The BPE algorithm behind GPT tokenizers. | None. | Section 3.2 + Algorithm 1. | BPE trainer (P3). | - | CORE | ☐
5 | SentencePiece | Kudo, Richardson | 2018 | 1 | W3 | https://arxiv.org/abs/1808.06226 | Language-independent tokenization; unigram LM alternative. | BPE paper. | Sections 2-3. | Train BPE vs unigram and compare. | - | CORE | ☐
6 | Lost in the Middle | Liu, Lin, Hewitt, Paranjape, Bevilacqua, Petroni, Liang | 2023 | 1 | W6 | https://arxiv.org/abs/2307.03172 | Position effects in long contexts - drives context ordering. | RAG basics. | Sections 2-4. | - | Position sweep on your RAG. | CORE | ☐
7 | Chain-of-Thought Prompting | Wei et al. | 2022 | 1 | W9 | https://arxiv.org/abs/2201.11903 | Reasoning traces as a capability lever. | Prompting. | Sections 2-3. | - | - | CORE | ☐
8 | Attention Is All You Need | Vaswani, Shazeer, Parmar, Uszkoreit, Jones, Gomez, Kaiser, Polosukhin | 2017 | 2 | W1 | https://arxiv.org/abs/1706.03762 | Defines the architecture everything else modifies. | Matrix multiplication, softmax, residual nets; the W1 attention concept note. | 3.1-3.2.3 (attention + multi-head), 3.5 (positional encoding), Table 3 ablations. | Scaled dot-product attention, MHA, sinusoidal PE (P1/P2). | Table 3 row (A): vary heads at fixed compute on a toy task. | CORE | ☐
9 | BERT: Pre-training of Deep Bidirectional Transformers | Devlin, Chang, Lee, Toutanova | 2018 | 2 | W2 | https://arxiv.org/abs/1810.04805 | Encoder-only counterpart; explains why bidirectional encoders still dominate embeddings/rerankers. | Transformer encoder; masked vs causal attention. | Sections 3.1-3.2 (MLM, NSP), Figure 1. | Masked-LM objective on your encoder (optional). | - | CORE | ☐
10 | Language Models are Unsupervised Multitask Learners (GPT-2) | Radford, Wu, Child, Luan, Amodei, Sutskever | 2019 | 2 | W2 | https://cdn.openai.com/better-language-models/language_models_are_unsupervised_multitask_learners.pdf | Zero-shot task transfer from pure LM; byte-level BPE; pre-norm. | GPT-1; byte-level BPE idea. | Sections 2.1-2.3 (data, input representation, model changes). | Byte-level BPE (P3). | - | CORE | ☐
11 | Root Mean Square Layer Normalization | Zhang, Sennrich | 2019 | 2 | W2 | https://arxiv.org/abs/1910.07467 | Why modern LLMs dropped mean-centering. | LayerNorm forward/backward. | Sections 2-3. | RMSNorm layer + test. | - | CORE | ☐
12 | Fast Transformer Decoding: One Write-Head is All You Need (MQA) | Shazeer | 2019 | 2 | W2 | https://arxiv.org/abs/1911.02150 | First paper to attack KV-cache bandwidth. | MHA; KV cache (W4 concept note helps). | Sections 2-3. | MQA as GQA special case. | - | CORE | ☐
13 | GQA: Training Generalized Multi-Query Transformer Models | Ainslie, Lee-Thorp, de Jong, Zemlyanskiy, Lebron, Sanghai | 2023 | 2 | W2 | https://arxiv.org/abs/2305.13245 | The KV-sharing scheme used by most current LLMs. | MQA paper. | Sections 2-3, Figure 2. | GQA attention. | - | CORE | ☐
14 | Language Models are Few-Shot Learners (GPT-3) | Brown et al. | 2020 | 2 | W3 | https://arxiv.org/abs/2005.14165 | In-context learning + the model-size table everyone quotes. | GPT-2; in-context learning idea. | Sections 2.1-2.3, Table 2.1, Figure 1.2. | - | - | CORE | ☐
15 | The Curious Case of Neural Text Degeneration | Holtzman, Buys, Du, Forbes, Choi | 2019 | 2 | W4 | https://arxiv.org/abs/1904.09751 | Why greedy/beam degenerate and why top-p works. | Softmax, logits, sampling basics. | Sections 3-5. | Top-p sampling. | Distinct-n vs perplexity plot. | CORE | ☐
16 | Mixtral of Experts | Jiang et al. | 2024 | 2 | W4 | https://arxiv.org/abs/2401.04088 | Open production MoE design. | Switch Transformer. | Section 2. | - | - | CORE | ☐
17 | Sentence-BERT | Reimers, Gurevych | 2019 | 2 | W5 | https://arxiv.org/abs/1908.10084 | Bi-encoder sentence embeddings. | BERT; cosine similarity. | Sections 3-4. | Bi-encoder fine-tune. | - | CORE | ☐
18 | Dense Passage Retrieval for Open-Domain QA | Karpukhin et al. | 2020 | 2 | W5 | https://arxiv.org/abs/2004.04906 | Dense retrieval with in-batch negatives beats BM25 in-domain. | SBERT; BM25 baseline. | Sections 3.1-3.2, 5. | In-batch negatives. | - | CORE | ☐
19 | BEIR: Heterogeneous Benchmark for Zero-shot IR | Thakur, Reimers, Ruckle, Srivastava, Gurevych | 2021 | 2 | W5 | https://arxiv.org/abs/2104.08663 | Shows BM25 is a strong zero-shot baseline; standard IR eval. | IR metrics (nDCG@10). | Sections 3-5, Table 2. | nDCG@10 harness. | BM25 nDCG@10 on SciFact within ~0.02 of the paper (Reproduction #3). | CORE | ☐
20 | Retrieval-Augmented Generation for Knowledge-Intensive NLP | Lewis et al. | 2020 | 2 | W6 | https://arxiv.org/abs/2005.11401 | Names and formalizes RAG. | DPR; seq2seq generation. | Sections 2.1-2.4. | - | - | CORE | ☐
21 | Precise Zero-Shot Dense Retrieval without Relevance Labels (HyDE) | Gao, Ma, Lin, Callan | 2022 | 2 | W6 | https://arxiv.org/abs/2212.10496 | Generate-then-retrieve query expansion. | Dense retrieval. | Section 3. | HyDE stage in P5. | - | CORE | ☐
22 | Judging LLM-as-a-Judge with MT-Bench and Chatbot Arena | Zheng et al. | 2023 | 2 | W7 | https://arxiv.org/abs/2306.05685 | Quantifies judge biases (position, verbosity, self-preference). | Pairwise comparison; Elo intuition. | Sections 3-4. | Pairwise judge with swap. | Measure position bias of your judge. | CORE | ☐
23 | G-Eval | Liu, Iter, Xu, Wang, Xu, Zhu | 2023 | 2 | W7 | https://arxiv.org/abs/2303.16634 | Rubric/CoT-based judging. | Prompting; rubric scoring. | Section 2. | Rubric judge. | - | CORE | ☐
24 | RAGAS: Automated Evaluation of RAG | Es, James, Espinosa-Anke, Schockaert | 2023 | 2 | W7 | https://arxiv.org/abs/2309.15217 | Faithfulness / answer relevance / context relevance definitions. | RAG pipeline; NLI/entailment intuition. | Section 3. | Your own faithfulness metric. | - | CORE | ☐
25 | Who Validates the Validators? | Shankar, Zamfirescu-Pereira, Hartmann, Parameswaran, Arawjo | 2024 | 2 | W7 | https://arxiv.org/abs/2404.12272 | Criteria drift; aligning judges with humans. | LLM-as-judge basics. | Sections 1, 4-6. | Judge calibration loop. | - | CORE | ☐
26 | tau-bench: Tool-Agent-User Interaction | Yao, Shinn, Razavi, Narasimhan | 2024 | 2 | W7 | https://arxiv.org/abs/2406.12045 | State-based agent evaluation and pass^k reliability. | Tool calling; agent loop. | Sections 3-4. | pass^k metric. | - | CORE | ☐
27 | LoRA: Low-Rank Adaptation | Hu et al. | 2021 | 2 | W8 | https://arxiv.org/abs/2106.09685 | Default PEFT method. | Matrix rank; fine-tuning. | Sections 4.1-4.2, 7. | LoRALinear from scratch. | Rank sweep + LR sweep (Reproduction #4 with 'LoRA Without Regret'). | CORE | ☐
28 | s1: Simple Test-Time Scaling | Muennighoff et al. | 2025 | 2 | W9 | https://arxiv.org/abs/2501.19393 | 1K SFT examples + budget forcing -> test-time scaling. | SFT; decoding control. | Sections 2-3. | Budget forcing at inference. | - | CORE | ☐
29 | ReAct: Synergizing Reasoning and Acting | Yao et al. | 2022 | 2 | W10 | https://arxiv.org/abs/2210.03629 | The thought -> action -> observation loop. | Tool calling; prompting. | Sections 2-3. | Raw agent loop. | - | CORE | ☐
30 | Reflexion | Shinn, Cassano, Berman, Gopinath, Narasimhan, Yao | 2023 | 2 | W10 | https://arxiv.org/abs/2303.11366 | Verbal self-reflection memory. | ReAct. | Section 3. | Self-critique step. | - | CORE | ☐
31 | MemGPT: Towards LLMs as Operating Systems | Packer et al. | 2023 | 2 | W10 | https://arxiv.org/abs/2310.08560 | Paging model for agent memory. | Context windows; retrieval. | Sections 2-3. | Memory tiers in P8. | - | CORE | ☐
32 | The FineWeb Datasets | Penedo et al. | 2024 | 2 | W12 | https://arxiv.org/abs/2406.17557 | Modern web-data filtering and dedup ablations. | Pretraining data basics; MinHash intuition. | Sections 3-4. | - | - | CORE | ☐
33 | An Image is Worth 16x16 Words (ViT) | Dosovitskiy et al. | 2020 | 2 | W12 | https://arxiv.org/abs/2010.11929 | Images as token sequences. | Transformer encoder; convolution. | Section 3.1. | Patch embedding. | - | CORE | ☐
34 | Learning Transferable Visual Models from Natural Language Supervision (CLIP) | Radford et al. | 2021 | 2 | W12 | https://arxiv.org/abs/2103.00020 | Contrastive image-text alignment. | InfoNCE; ViT. | Sections 2.1-2.5, Figure 3 pseudocode. | Symmetric CLIP loss. | Zero-shot accuracy on a small dataset. | CORE | ☐
35 | Visual Instruction Tuning (LLaVA) | Liu, Li, Wu, Lee | 2023 | 2 | W12 | https://arxiv.org/abs/2304.08485 | Projection-layer VLM recipe. | CLIP; instruction tuning. | Sections 3-4. | - | - | CORE | ☐
36 | Robust Speech Recognition via Large-Scale Weak Supervision (Whisper) | Radford, Kim, Xu, Brockman, McLeavey, Sutskever | 2022 | 2 | W12 | https://arxiv.org/abs/2212.04356 | Seq2seq ASR at scale. | Encoder-decoder transformers; spectrograms. | Sections 2-3. | - | - | CORE | ☐
37 | SWE-bench | Jimenez, Yang, Wettig, Yao, Pei, Press, Narasimhan | 2023 | 2 | W13 | https://arxiv.org/abs/2310.06770 | The benchmark your capstone runs on. | Agent loop; unit tests; git patches. | Sections 2-3. | Harness integration. | Resolve rate on a Lite/Verified subset. | CORE | ☐
38 | RouteLLM | Ong et al. | 2024 | 2 | W13 | https://arxiv.org/abs/2406.18665 | Learned strong/weak model routing. | LLM-as-judge; classifiers. | Sections 3-4. | Router in capstone. | - | CORE | ☐
39 | On Layer Normalization in the Transformer Architecture | Xiong et al. | 2020 | 3 | W2 | https://arxiv.org/abs/2002.04745 | Explains why pre-norm trains without warmup tricks. | Residual streams, LayerNorm, LR warmup. | Sections 1, 3 (skip proofs on first pass). | Pre-norm vs post-norm switch. | W3 ablation: post-norm diverges at high LR, pre-norm does not. | CORE | ☐
40 | RoFormer: Enhanced Transformer with Rotary Position Embedding | Su, Lu, Pan, Murtadha, Wen, Liu | 2021 | 3 | W2 | https://arxiv.org/abs/2104.09864 | RoPE is the default positional scheme in open LLMs. | Complex numbers / 2-D rotations; dot-product attention. | Sections 3.1-3.4. | RoPE + numerical relative-position test. | - | CORE | ☐
41 | Scaling Laws for Neural Language Models | Kaplan et al. | 2020 | 3 | W4 | https://arxiv.org/abs/2001.08361 | Power-law relationships between loss and N, D, C. | Log-log plots, power laws, C ~ 6ND. | Sections 1-3, Figures 1-4. | - | Fit L(N) on your runs. | CORE | ☐
42 | Training Compute-Optimal Large Language Models (Chinchilla) | Hoffmann et al. | 2022 | 3 | W4 | https://arxiv.org/abs/2203.15556 | Corrected Kaplan: scale data with parameters (~20 tokens/param). | Kaplan scaling laws. | Sections 3.1-3.3 (three approaches), Table 3. | C = 6ND calculator. | Mini IsoFLOP study (Reproduction #2). | CORE | ☐
43 | Switch Transformers | Fedus, Zoph, Shazeer | 2021 | 3 | W4 | https://arxiv.org/abs/2101.03961 | Canonical sparse MoE routing + load balancing. | FFN block; softmax routing. | Sections 2.1-2.2 (routing, aux loss). | Top-k router + aux loss. | Dense vs MoE at equal active params. | CORE | ☐
44 | Representation Learning with Contrastive Predictive Coding (InfoNCE) | van den Oord, Li, Vinyals | 2018 | 3 | W5 | https://arxiv.org/abs/1807.03748 | Origin of the InfoNCE loss used by every embedding model. | Softmax cross-entropy; mutual information intuition. | Section 2.3 (InfoNCE). | InfoNCE with in-batch negatives. | - | CORE | ☐
45 | Product Quantization for Nearest Neighbor Search | Jegou, Douze, Schmid | 2011 | 3 | W5 | https://doi.org/10.1109/TPAMI.2010.57 | Compression behind IVF-PQ in FAISS and most vector DBs. | k-means; Euclidean distance decomposition. | Sections II-III (PQ, ADC/SDC). | PQ + ADC in NumPy. | Recall vs code size curve. | CORE | ☐
46 | Efficient and Robust ANN Search using HNSW Graphs | Malkov, Yashunin | 2016 | 3 | W5 | https://arxiv.org/abs/1603.09320 | Default ANN index in pgvector/Qdrant/most DBs. | Graph search, greedy/beam search; small-world graphs. | Sections 3-4, Algorithms 1-4. | NSW/HNSW search. | Recall-latency vs M/efSearch. | CORE | ☐
47 | The Faiss Library | Douze et al. | 2024 | 3 | W5 | https://arxiv.org/abs/2401.08281 | Map of the whole ANN design space by its authors. | PQ + HNSW papers. | Sections 3-5 (skim). | - | - | CORE | ☐
48 | ColBERT: Late Interaction over BERT | Khattab, Zaharia | 2020 | 3 | W6 | https://arxiv.org/abs/2004.12832 | Multi-vector retrieval (MaxSim). | BERT; bi-encoder vs cross-encoder. | Section 3. | MaxSim reranker. | - | CORE | ☐
49 | M3-Embedding (BGE-M3) | Chen, Xiao, Zhang, Luo, Lian, Liu | 2024 | 3 | W6 | https://arxiv.org/abs/2402.03216 | Dense + sparse + multi-vector from one model. | Dense, sparse (lexical weights) and multi-vector retrieval. | Sections 3-4. | Use its three heads in P5. | - | CORE | ☐
50 | Self-RAG | Asai, Wu, Wang, Sil, Hajishirzi | 2023 | 3 | W6 | https://arxiv.org/abs/2310.11511 | Retrieval-on-demand + self-critique tokens. | RAG; instruction tuning. | Abstract, Section 3 overview. | - | - | CORE | ☐
51 | From Local to Global: A Graph RAG Approach | Edge et al. | 2024 | 3 | W6 | https://arxiv.org/abs/2404.16130 | Entity graph + community summaries for global questions. | RAG; community detection (Leiden) at intuition level. | Sections 2-3. | Optional entity graph. | - | CORE | ☐
52 | Training LMs to Follow Instructions with Human Feedback (InstructGPT) | Ouyang et al. | 2022 | 3 | W8 | https://arxiv.org/abs/2203.02155 | The SFT -> RM -> PPO recipe. | SFT; reward models; PPO at intuition level. | Sections 3.1-3.5, Figure 2. | SFT with loss masking; RM loss. | - | CORE | ☐
53 | QLoRA | Dettmers, Pagnoni, Holtzman, Zettlemoyer | 2023 | 3 | W8 | https://arxiv.org/abs/2305.14314 | Fine-tune 7-70B on one GPU (NF4, double quant, paged optimizers). | LoRA; quantization basics (absmax, blocks). | Section 3. | NF4 quantize/dequantize toy. | - | CORE | ☐
54 | Deep RL from Human Preferences | Christiano, Leike, Brown, Martic, Legg, Amodei | 2017 | 3 | W9 | https://arxiv.org/abs/1706.03741 | Origin of learning rewards from comparisons. | Bradley-Terry model; RL basics. | Sections 1-2. | Bradley-Terry RM loss. | - | CORE | ☐
55 | DeepSeek-R1 | DeepSeek-AI | 2025 | 3 | W9 | https://arxiv.org/abs/2501.12948 | RL-from-base (R1-Zero), emergent long CoT, distillation. | GRPO; SFT; distillation. | Sections 2-3. | - | - | CORE | ☐
56 | Tulu 3: Pushing Frontiers in Open Post-Training | Lambert et al. | 2024 | 3 | W9 | https://arxiv.org/abs/2411.15124 | Fully open SFT -> DPO -> RLVR recipe. | SFT, DPO, RLVR. | RLVR section + data sections (skim). | - | - | CORE | ☐
57 | Efficient Memory Management for LLM Serving with PagedAttention | Kwon et al. | 2023 | 3 | W11 | https://arxiv.org/abs/2309.06180 | KV-cache paging + continuous batching. | KV cache; virtual memory paging; batching. | Sections 3-4, 6. | - | Throughput vs static batching (Reproduction #6). | CORE | ☐
58 | Sarathi-Serve (chunked prefill) | Agrawal et al. | 2024 | 3 | W11 | https://arxiv.org/abs/2403.02310 | Prefill/decode interference and chunked prefill. | Prefill vs decode; continuous batching. | Sections 2-4. | - | - | CORE | ☐
59 | Fast Inference from Transformers via Speculative Decoding | Leviathan, Kalman, Matias | 2022 | 3 | W11 | https://arxiv.org/abs/2211.17192 | Exact speedup with a draft model. | Rejection sampling; autoregressive decoding. | Sections 2-3. | Speculative sampling. | Acceptance-rate vs k. | CORE | ☐
60 | LLM.int8() | Dettmers, Lewis, Belkada, Zettlemoyer | 2022 | 3 | W11 | https://arxiv.org/abs/2208.07339 | Outlier features and why naive INT8 breaks. | Integer quantization; matmul decomposition. | Sections 3-4. | - | - | CORE | ☐
61 | AWQ: Activation-aware Weight Quantization | Lin et al. | 2023 | 3 | W11 | https://arxiv.org/abs/2306.00978 | Protect salient channels via scaling. | Quantization; activation statistics. | Section 3. | - | AWQ vs BF16 quality/speed in P10. | CORE | ☐
62 | ZeRO: Memory Optimizations Toward Training Trillion Parameter Models | Rajbhandari, Rasley, Ruwase, He | 2019 | 3 | W12 | https://arxiv.org/abs/1910.02054 | Optimizer/gradient/parameter sharding (basis of FSDP). | Adam state memory; data parallelism; all-reduce. | Sections 4-5. | - | Memory table for 8B model. | CORE | ☐
63 | Megatron-LM | Shoeybi et al. | 2019 | 3 | W12 | https://arxiv.org/abs/1909.08053 | Tensor parallelism for transformer blocks. | Matmul partitioning; all-reduce. | Section 3. | - | - | CORE | ☐
64 | ColPali: Efficient Document Retrieval with VLMs | Faysse et al. | 2024 | 3 | W12 | https://arxiv.org/abs/2407.01449 | OCR-free page retrieval with multi-vector VLM embeddings. | ColBERT MaxSim; VLMs. | Sections 3-4. | Page-image retrieval in P11. | - | CORE | ☐
65 | Proximal Policy Optimization Algorithms | Schulman, Wolski, Dhariwal, Radford, Klimov | 2017 | 4 | W9 | https://arxiv.org/abs/1707.06347 | Clipped surrogate objective used in RLHF and GRPO. | Policy gradients; advantage; KL divergence. | Sections 2-5. | PPO clip loss. | - | CORE | ☐
66 | Direct Preference Optimization | Rafailov, Sharma, Mitchell, Ermon, Manning, Finn | 2023 | 4 | W9 | https://arxiv.org/abs/2305.18290 | RLHF without a reward model or RL loop. | RLHF objective with KL penalty; Bradley-Terry; log-probs of sequences. | Sections 4-5 (derivation), Appendix A.1. | DPO loss from scratch. | DPO vs SFT win-rate on your eval. | CORE | ☐
67 | DeepSeekMath (introduces GRPO) | Shao et al. | 2024 | 4 | W9 | https://arxiv.org/abs/2402.03300 | GRPO: critic-free PPO with group baselines. | PPO. | Section 4 (4.1-4.2). | GRPO loss. | - | CORE | ☐
68 | Understanding R1-Zero-Like Training: A Critical Perspective (Dr. GRPO) | Liu et al. | 2025 | 4 | W9 | https://arxiv.org/abs/2503.20783 | Finds GRPO's length bias; simple fix. | GRPO objective in detail. | Sections 2-3. | Dr. GRPO normalization flag. | Length growth with/without fix (Reproduction #5). | CORE | ☐
69 | DAPO: Open-Source LLM RL System at Scale | Yu et al. | 2025 | 4 | W9 | https://arxiv.org/abs/2503.14476 | Clip-higher, dynamic sampling, token-level loss, overlong shaping. | GRPO; PPO clipping. | Section 3. | Clip-higher option. | - | CORE | ☐
70 | FlashAttention | Dao, Fu, Ermon, Rudra, Re | 2022 | 4 | W11 | https://arxiv.org/abs/2205.14135 | IO-aware exact attention - the canonical 'memory, not FLOPs' lesson. | GPU memory hierarchy (HBM vs SRAM); softmax; roofline. | Sections 2-3 (algorithm, IO analysis). | Tiled online-softmax attention in PyTorch. | HBM traffic estimate vs naive. | CORE | ☐
71 | GPTQ | Frantar, Ashkboos, Hoefler, Alistarh | 2022 | 4 | W11 | https://arxiv.org/abs/2210.17323 | Second-order post-training weight quantization. | Quantization; Hessian / second-order intuition. | Sections 3-4 (idea level). | - | - | CORE | ☐
72 | GPipe | Huang et al. | 2018 | 3 | 2027 | https://arxiv.org/abs/1811.06965 | Pipeline parallelism + micro-batching. | Data parallelism; micro-batching. | Section 2. | - | - | EXT | ☐
73 | Let's Verify Step by Step | Lightman et al. | 2023 | 3 | 2027 | https://arxiv.org/abs/2305.20050 | Process vs outcome reward models. | Reward models; step-level labels. | Sections 2-4. | - | - | EXT | ☐
74 | Constitutional AI | Bai et al. | 2022 | 3 | 2027 | https://arxiv.org/abs/2212.08073 | AI feedback instead of human labels. | RLHF; critique-revision. | Sections 3-4. | - | - | EXT | ☐
75 | DeepSeekMoE | Dai et al. | 2024 | 3 | 2027 | https://arxiv.org/abs/2401.06066 | Fine-grained + shared experts. | Switch/Mixtral MoE. | Sections 3-4. | - | - | EXT | ☐
76 | Qwen3 Technical Report | Qwen Team | 2025 | 3 | 2027 | https://arxiv.org/abs/2505.09388 | Thinking/non-thinking modes, MoE, post-training pipeline. | Modern LLM architecture + post-training. | Architecture + post-training sections. | - | - | EXT | ☐
77 | ColBERTv2 | Santhanam et al. | 2021 | 3 | 2027 | https://arxiv.org/abs/2112.01488 | Residual compression for late interaction. | ColBERT; residual quantization. | Section 3. | - | - | EXT | ☐
78 | Sigmoid Loss for Language Image Pre-Training (SigLIP) | Zhai, Mustafa, Kolesnikov, Beyer | 2023 | 3 | 2027 | https://arxiv.org/abs/2303.15343 | Sigmoid vs softmax contrastive loss. | CLIP. | Sections 2-3. | - | - | EXT | ☐
79 | FlashAttention-2 | Dao | 2023 | 4 | 2027 | https://arxiv.org/abs/2307.08691 | Work partitioning improvements; basis of CS336 A2. | FlashAttention; GPU warps/thread blocks. | Sections 3-4. | Triton FA2 (CS336 A2). | - | EXT | ☐
80 | Generalized Advantage Estimation | Schulman, Moritz, Levine, Jordan, Abbeel | 2015 | 4 | 2027 | https://arxiv.org/abs/1506.02438 | Variance reduction for policy gradients. | Value functions; TD(lambda). | Sections 3-4. | GAE in a PPO trainer. | - | EXT | ☐
81 | DeepSeek-V3 Technical Report | DeepSeek-AI | 2024 | 4 | 2027 | https://arxiv.org/abs/2412.19437 | MLA, auxiliary-loss-free MoE balancing, FP8 training, MTP - a frontier training systems case study. | MoE, MLA, FP8, pipeline parallelism. | Sections 2-3. | - | - | EXT | ☐

## Resources
Kind | Title | By / channel | Duration | Link | Week(s) | Why / notes
PRIMARY | Understanding Deep Learning (Prince), ch. 5-9 - targeted revision |  |  | https://udlbook.github.io/udlbook/ | W1
PRIMARY | CS336 2026 Lecture 2 trace - PyTorch, einops, resource accounting |  |  | https://cs336.stanford.edu/lectures/?trace=lecture_02 | W1
PRIMARY | Concept note: attention & transformer shapes |  |  | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/01-attention-and-transformer.md | W1, W2
PRIMARY | The Illustrated Transformer (Alammar) |  |  | https://jalammar.github.io/illustrated-transformer/ | W1
SECONDARY | The Matrix Calculus You Need for Deep Learning |  |  | https://explained.ai/matrix-calculus/ | W1
SECONDARY | The Annotated Transformer |  |  | https://nlp.seas.harvard.edu/annotated-transformer/ | W1, W2
REFERENCE | How to Read a Paper (Keshav) |  |  | http://ccr.sigcomm.org/online/files/p83-keshavA.pdf | W1
VIDEO | Building makemore Part 4: Becoming a Backprop Ninja | Andrej Karpathy | 1h55m | https://www.youtube.com/watch?v=q8SA3rM6ckI | W1 | Only if the diagnostic shows you can't write a manual backward pass; the best drill for gradient flow. (P0 backprop)
VIDEO | Transformers, the tech behind LLMs ¦ DL5 | 3Blue1Brown | 27m | https://www.youtube.com/watch?v=wjZofJX0v4M | W1 | Geometric intuition for embeddings and next-token prediction before any equations. (P1 intuition)
VIDEO | Attention in transformers, step-by-step ¦ DL6 | 3Blue1Brown | 26m | https://www.youtube.com/watch?v=eMlx5fFNoYc | W1 | Clearest visual explanation of Q, K, V and why masking exists. (P1 attention)
VIDEO | Let's build GPT (Karpathy) - code along | Andrej Karpathy | 1h56m | https://www.youtube.com/watch?v=kCc8FmEb1nY | W2 | Fastest route from bigram model to a working decoder block; you will diverge from it with modern components. (P1 implementation)
PRIMARY | CS336 2026 Lecture 3 - Architectures & hyperparameters (slides) |  |  | https://github.com/stanford-cs336/lectures/blob/main/lecture_03.pdf | W2
SECONDARY | The Big LLM Architecture Comparison (Raschka, updated 2026) |  |  | https://magazine.sebastianraschka.com/p/the-big-llm-architecture-comparison | W2
REFERENCE | Build a Large Language Model (From Scratch) code |  |  | https://github.com/rasbt/LLMs-from-scratch | W2
VIDEO | Stanford CS336 Spring 2026 - Lecture 3: Architectures | Tatsu Hashimoto (Stanford) | ~1h20m | https://www.youtube.com/watch?v=lVynu4bo1rY | W2 | Evidence-based survey of pre-norm, RMSNorm, SwiGLU, RoPE, GQA and hyperparameter conventions across real LLMs. (P1 architecture)
VIDEO | LLaMA explained: KV-Cache, RoPE, RMS Norm, GQA, SwiGLU | Umar Jamil | ~1h10m | https://www.youtube.com/watch?v=Mn_9W1nCFLo | W2 | Best derivation-level explanation of RoPE and GQA with code. (P1 RoPE/GQA)
PRIMARY | CS336 Assignment 1 (Basics) - handout + tests are the spec |  |  | https://github.com/stanford-cs336/assignment1-basics | W3
VIDEO | Let's build the GPT Tokenizer (Karpathy) + minbpe | Andrej Karpathy | 2h13m | https://www.youtube.com/watch?v=zduSFxRajkE | W3 | Explains byte-level BPE, regex pre-tokenization, special tokens and the weird failures tokenization causes. (P2 tokenization)
PRIMARY | Concept note: prompt -> next token (loss, perplexity sections) |  |  | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/02-prompt-to-next-token.md | W3, W4
SECONDARY | minbpe reference implementation |  |  | https://github.com/karpathy/minbpe | W3
SECONDARY | nanoGPT reference |  |  | https://github.com/karpathy/nanoGPT | W3
REFERENCE | A Recipe for Training Neural Networks (Karpathy) |  |  | http://karpathy.github.io/2019/04/25/recipe/ | W3
VIDEO | Stanford CS336 Spring 2026 - Lecture 1: Overview, Tokenization | Percy Liang (Stanford) | ~1h20m | https://www.youtube.com/watch?v=JuoVZkPBiKk | W3 | Frames the whole LM pipeline and the tokenizer design space used in A1. (P2 tokenization)
PRIMARY | CS336 2026 Lecture 10 trace - Inference |  |  | https://cs336.stanford.edu/lectures/?trace=lecture_10 | W4
PRIMARY | CS336 2026 Lecture 9 slides - Scaling laws |  |  | https://github.com/stanford-cs336/lectures/blob/main/lecture_09.pdf | W4
PRIMARY | CS336 2026 Lecture 4 slides - Attention alternatives & MoE |  |  | https://github.com/stanford-cs336/lectures/blob/main/lecture_04.pdf | W4
SECONDARY | Transformer Inference Arithmetic (kipply) |  |  | https://kipply.github.io/blog/transformer-inference-arithmetic/ | W4
SECONDARY | A Visual Guide to Mixture of Experts (Grootendorst) |  |  | https://newsletter.maartengrootendorst.com/p/a-visual-guide-to-mixture-of-experts | W4
SECONDARY | LLM Visualization (Bycroft) - 3D walk through one token |  |  | https://bbycroft.net/llm | W4
VIDEO | CS336 2026 playlist (lectures 4, 9, 10, 11) | Liang / Hashimoto (Stanford) | ~1h20m each | https://www.youtube.com/playlist?list=PLoROMvodv4rMqXOcazWaTUHhq-yembLCV | W4, W7, W8, W9, W12 | Collective communication and DP/TP/PP trade-offs with real numbers. (P11 distributed)
VIDEO | Stanford CS229: Building Large Language Models (LLMs) | Yann Dubois (Stanford) | ~1h44m | https://www.youtube.com/watch?v=9vM4p9NN0Ts | W4 | Optional single-sitting overview tying pretraining, scaling laws, evaluation and post-training together. (P2 overview)
PRIMARY | Concept note: retrieval & vector search |  |  | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/03-retrieval-and-vector-search.md | W5
PRIMARY | Introduction to Information Retrieval - ch. 6 & 11.4.3 (BM25) |  |  | https://nlp.stanford.edu/IR-book/html/htmledition/irbook.html | W5
PRIMARY | Faiss: The Missing Manual (Pinecone) - indexes, PQ, HNSW chapters |  |  | https://www.pinecone.io/learn/series/faiss/ | W5
SECONDARY | bm25s (fast reference BM25) |  |  | https://github.com/xhluca/bm25s | W5
SECONDARY | The Faiss library paper |  |  | https://arxiv.org/abs/2401.08281 | W5
REFERENCE | pgvector |  |  | https://github.com/pgvector/pgvector | W5
REFERENCE | Qdrant docs |  |  | https://qdrant.tech/documentation/ | W5
REFERENCE | Sentence-Transformers docs |  |  | https://sbert.net/ | W5
VIDEO | HNSW for Vector Search Explained and Implemented with Faiss | James Briggs | ~35m | https://www.youtube.com/watch?v=QvKMwLjdK-s | W5 | Visual walk-through of the HNSW layers and parameters before you read the paper. (P3 ANN)
PRIMARY | RAG paper (Lewis et al.) |  |  | https://arxiv.org/abs/2005.11401 | W6
PRIMARY | Beyond the Basics of RAG (Clavie) - notes page |  |  | https://parlance-labs.com/education/rag/ben.html | W6
PRIMARY | Introducing Contextual Retrieval (Anthropic) |  |  | https://www.anthropic.com/news/contextual-retrieval | W6
SECONDARY | Docling docs (document parsing) |  |  | https://docling-project.github.io/docling/ | W6
SECONDARY | Concept note: RAG & evaluation metrics |  |  | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/04-rag-and-evaluation-metrics.md | W6, W7
REFERENCE | BGE-M3 paper |  |  | https://arxiv.org/abs/2402.03216 | W6
REFERENCE | ColBERT paper |  |  | https://arxiv.org/abs/2004.12832 | W6
VIDEO | Stanford CS25: V3 - Retrieval Augmented Language Models | Douwe Kiela (Stanford CS25) | 1h19m | https://www.youtube.com/watch?v=mE7IDf2SmJg | W6 | Research-level map of RAG: retriever/generator training, architectures, open problems. (P4 foundations)
VIDEO | Beyond the Basics of Retrieval for Augmenting Generation | Ben Clavie (Answer.AI) | ~1h | https://www.youtube.com/watch?v=0nA5QG3087g | W6 | Practitioner's 'MVP++': BM25 + bi-encoder + reranker + metadata filters, and how to evaluate. (P4 advanced retrieval)
PRIMARY | Your AI Product Needs Evals (Husain) |  |  | https://hamel.dev/blog/posts/evals/ | W7
PRIMARY | Using LLM-as-a-Judge: A Complete Guide (Husain) |  |  | https://hamel.dev/blog/posts/llm-judge/ | W7
PRIMARY | Demystifying evals for AI agents (Anthropic) |  |  | https://www.anthropic.com/engineering/demystifying-evals-for-ai-agents | W7, W13
SECONDARY | Evaluating the Effectiveness of LLM-Evaluators (Eugene Yan) |  |  | https://eugeneyan.com/writing/llm-evaluators/ | W7
SECONDARY | LLM Evaluation Guidebook (Hugging Face) |  |  | https://huggingface.co/spaces/OpenEvals/evaluation-guidebook | W7
SECONDARY | CS336 2026 Lecture 12 trace - Evaluation |  |  | https://cs336.stanford.edu/lectures/?trace=lecture_12 | W7
REFERENCE | Ragas metric definitions |  |  | https://docs.ragas.io/en/stable/concepts/metrics/available_metrics/ | W7
REFERENCE | Inspect (UK AISI) eval framework |  |  | https://inspect.aisi.org.uk/ | W7
REFERENCE | lm-evaluation-harness |  |  | https://github.com/EleutherAI/lm-evaluation-harness | W7
PRIMARY | Hugging Face LLM Course ch. 11 - Supervised fine-tuning |  |  | https://huggingface.co/learn/llm-course/chapter11/1 | W8
PRIMARY | CS336 2026 Lecture 15 slides - Mid/post-training (SFT/RLHF) |  |  | https://github.com/stanford-cs336/lectures/blob/main/lecture_15.pdf | W8
PRIMARY | LoRA Without Regret (Thinking Machines) |  |  | https://thinkingmachines.ai/blog/lora/ | W8
PRIMARY | Concept note: post-training math |  |  | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/05-post-training-math.md | W8, W9
SECONDARY | Transformers chat templates docs |  |  | https://huggingface.co/docs/transformers/chat_templating | W8
SECONDARY | TRL SFTTrainer docs |  |  | https://huggingface.co/docs/trl/sft_trainer | W8
SECONDARY | Unsloth fine-tuning guide |  |  | https://unsloth.ai/docs/get-started/fine-tuning-llms-guide | W8
SECONDARY | smol-course |  |  | https://github.com/huggingface/smol-course | W8
REFERENCE | A Visual Guide to Quantization (Grootendorst) |  |  | https://newsletter.maartengrootendorst.com/p/a-visual-guide-to-quantization | W8, W11
REFERENCE | TRL: LoRA without regret recipe |  |  | https://huggingface.co/docs/trl/en/lora_without_regret | W8
PRIMARY | OpenAI Spinning Up - Parts 1 and 3 |  |  | https://spinningup.openai.com/en/latest/ | W9
PRIMARY | RLHF Book (Lambert) |  |  | https://rlhfbook.com/ | W9
PRIMARY | CS336 2026 Lecture 16 slides - Post-training: RLVR |  |  | https://github.com/stanford-cs336/lectures/blob/main/lecture_16.pdf | W9
SECONDARY | HF LLM Course ch. 12 - Build reasoning models (GRPO) |  |  | https://huggingface.co/learn/llm-course/chapter12 | W9
SECONDARY | Build a Reasoning Model (From Scratch) code |  |  | https://github.com/rasbt/reasoning-from-scratch | W9
SECONDARY | Why We Think (Weng) |  |  | https://lilianweng.github.io/posts/2025-05-01-thinking/ | W9
SECONDARY | Reward Hacking in RL (Weng) |  |  | https://lilianweng.github.io/posts/2024-11-28-reward-hacking/ | W9
REFERENCE | CS336 Assignment 5 (GRPO on OLMo-2 1B) - full version deferred to 2027 |  |  | https://github.com/stanford-cs336/assignment5-alignment | W9
VIDEO | L3 Policy Gradients and Advantage Estimation (Foundations of Deep RL) | Pieter Abbeel | ~1h | https://www.youtube.com/watch?v=AKbX1Zvo7r8 | W9 | Compact, rigorous policy-gradient derivation; watch L4 (TRPO/PPO) from the same playlist next. (P12 policy gradients)
VIDEO | Reinforcement Learning from Human Feedback explained with math derivations and the PyTorch code | Umar Jamil | ~2h | https://www.youtube.com/watch?v=qGyFrqc34yc | W9 | Walks from policy gradients to PPO-based RLHF with code; watch the PPO + RLHF sections. (P12 RLHF/PPO)
VIDEO | Direct Preference Optimization (DPO) explained: Bradley-Terry model, log probabilities, math | Umar Jamil | ~50m | https://www.youtube.com/watch?v=hvGa5Mba4c8 | W9 | Line-by-line derivation of the DPO loss. (P6 DPO)
PRIMARY | Building effective agents (Anthropic) |  |  | https://www.anthropic.com/engineering/building-effective-agents | W10
PRIMARY | Effective context engineering for AI agents (Anthropic) |  |  | https://www.anthropic.com/engineering/effective-context-engineering-for-ai-agents | W10, W13
PRIMARY | MCP specification 2026-07-28 (current) |  |  | https://modelcontextprotocol.io/specification/2026-07-28 | W10
PRIMARY | MCP 2026-07-28 release notes (what changed: stateless core, deprecations) |  |  | https://blog.modelcontextprotocol.io/posts/2026-07-28/ | W10
SECONDARY | Writing effective tools for agents (Anthropic) |  |  | https://www.anthropic.com/engineering/writing-tools-for-agents | W10
SECONDARY | How we built our multi-agent research system (Anthropic) |  |  | https://www.anthropic.com/engineering/multi-agent-research-system | W10
SECONDARY | LLM Powered Autonomous Agents (Weng) |  |  | https://lilianweng.github.io/posts/2023-06-23-agent/ | W10
SECONDARY | LangChain Academy - Introduction to LangGraph (free) |  |  | https://academy.langchain.com/courses/intro-to-langgraph | W10
SECONDARY | Hugging Face MCP Course |  |  | https://huggingface.co/learn/mcp-course/en/unit0/introduction | W10
SECONDARY | Hugging Face Agents Course |  |  | https://huggingface.co/learn/agents-course/en/unit0/introduction | W10
REFERENCE | LangGraph docs |  |  | https://docs.langchain.com/oss/python/langgraph/overview | W10
REFERENCE | LangChain middleware docs |  |  | https://docs.langchain.com/oss/python/langchain/middleware/overview | W10
REFERENCE | LangChain create_agent reference |  |  | https://reference.langchain.com/python/langchain/agents/factory/create_agent | W10
REFERENCE | LangSmith evaluation docs |  |  | https://docs.langchain.com/langsmith/evaluation | W10
REFERENCE | HF Agents Course - LangGraph unit |  |  | https://huggingface.co/learn/agents-course/unit2/langgraph/introduction | W10
REFERENCE | OpenAI Agents SDK docs |  |  | https://openai.github.io/openai-agents-python/ | W10
REFERENCE | LlamaIndex Workflows docs |  |  | https://developers.llamaindex.ai/python/framework/module_guides/workflow/ | W10
REFERENCE | smolagents docs |  |  | https://huggingface.co/docs/smolagents | W10
REFERENCE | OWASP Top 10 for LLM apps |  |  | https://genai.owasp.org/llm-top-10/ | W10
REFERENCE | The lethal trifecta (Willison) |  |  | https://simonwillison.net/2025/Jun/16/the-lethal-trifecta/ | W10
REFERENCE | mini-swe-agent (100-line reference agent) |  |  | https://github.com/SWE-agent/mini-swe-agent | W10, W13
VIDEO | How We Build Effective Agents | Barry Zhang (Anthropic) - AI Engineer Summit | ~15m | https://www.youtube.com/watch?v=D7_ipDqhtwk | W10 | Three principles: don't build agents for everything, keep them simple, think like your agent. (P7 design)
PRIMARY | Modal GPU Glossary |  |  | https://modal.com/gpu-glossary | W11
PRIMARY | How to Scale Your Model - All About Rooflines (Google DeepMind) |  |  | https://jax-ml.github.io/scaling-book/roofline/ | W11
PRIMARY | Making Deep Learning Go Brrrr (Horace He) |  |  | https://horace.io/brrr_intro.html | W11
PRIMARY | Inside vLLM: Anatomy of a High-Throughput Inference System (Gordic) |  |  | https://www.aleksagordic.com/blog/vllm | W11
PRIMARY | Concept note: GPU & inference math |  |  | https://github.com/anshu8830/anshu/blob/main/curriculum/concepts/06-gpu-and-inference-math.md | W11
SECONDARY | CS336 2026 Lecture 5 slides - GPUs/TPUs |  |  | https://github.com/stanford-cs336/lectures/blob/main/lecture_05.pdf | W11
SECONDARY | CS336 2026 Lecture 6 trace - Kernels, Triton |  |  | https://cs336.stanford.edu/lectures/?trace=lecture_06 | W11
SECONDARY | Triton tutorials |  |  | https://triton-lang.org/main/getting-started/tutorials/ | W11
REFERENCE | vLLM docs - automatic prefix caching |  |  | https://docs.vllm.ai/en/stable/design/prefix_caching/ | W11
REFERENCE | TensorRT-LLM docs |  |  | https://nvidia.github.io/TensorRT-LLM/ | W11
REFERENCE | GPU MODE lectures (code + slides) |  |  | https://github.com/gpu-mode/lectures | W11
VIDEO | FlashAttention - Tri Dao ¦ Stanford MLSys #67 | Tri Dao (Stanford MLSys Seminar) | ~1h | https://www.youtube.com/watch?v=gMOAud7hZg4 | W11 | The author explains IO-awareness, tiling and recomputation. (P9 FlashAttention)
VIDEO | Fast LLM Serving with vLLM and PagedAttention | vLLM authors (Woosuk Kwon, Zhuohan Li) | ~30-40m | https://www.youtube.com/watch?v=Oq2SN7uutbQ | W11 | Why KV-cache fragmentation limits batch size and how paging fixes it. (P9 serving)
VIDEO | Speculative Decoding: When Two LLMs are Faster than One | Efficient NLP | ~12m | https://www.youtube.com/watch?v=S-8yr_RibJ4 | W11 | Short, precise explanation of the acceptance rule. (P9 speculative decoding)
VIDEO | Flash Attention derived and coded from first principles with Triton (Python) | Umar Jamil | ~7h | https://www.youtube.com/watch?v=zy8ChVd_oTM | W11 | Optional deep dive (2027 track): derive and write FA in Triton, incl. backward pass. (P9 kernels (stretch))
PRIMARY | The Ultra-Scale Playbook (Hugging Face) |  |  | https://huggingface.co/spaces/nanotron/ultrascale-playbook | W12
PRIMARY | Understanding Multimodal LLMs (Raschka) |  |  | https://magazine.sebastianraschka.com/p/understanding-multimodal-llms | W12
PRIMARY | Vision Language Models (Better, faster, stronger) - HF 2025 |  |  | https://huggingface.co/blog/vlms-2025 | W12
PRIMARY | nanoVLM (repo + blog) |  |  | https://github.com/huggingface/nanoVLM | W12
SECONDARY | CS336 2026 Lecture 7 trace + Lecture 8 slides - Parallelism |  |  | https://cs336.stanford.edu/lectures/?trace=lecture_07 | W12
SECONDARY | CS336 2026 Lectures 13-14 traces - Data |  |  | https://cs336.stanford.edu/lectures/?trace=lecture_14 | W12
SECONDARY | picotron (4D parallelism in <300 lines/file) |  |  | https://github.com/huggingface/picotron | W12
SECONDARY | HF Computer Vision Course - CLIP unit |  |  | https://huggingface.co/learn/computer-vision-course/en/unit4/multimodal-models/clip-and-relatives/clip | W12
SECONDARY | ColPali blog |  |  | https://huggingface.co/blog/manu/colpali | W12
REFERENCE | The Smol Training Playbook |  |  | https://huggingface.co/spaces/HuggingFaceTB/smol-training-playbook | W12
REFERENCE | ML Engineering Open Book (Bekman) |  |  | https://github.com/stas00/ml-engineering | W12
REFERENCE | HF Audio Course - TTS unit |  |  | https://huggingface.co/learn/audio-course/en/chapter6/introduction | W12
REFERENCE | CS336 2026 Lecture 17 trace - multimodality |  |  | https://cs336.stanford.edu/lectures/?trace=lecture_17 | W12
VIDEO | Coding a Multimodal (Vision) Language Model from scratch in PyTorch | Umar Jamil | ~5h45m | https://www.youtube.com/watch?v=vAmKB7iPkWw | W12 | Watch the SigLIP encoder, projector and token-merging sections (~2h) - exactly how images become LM tokens. (P10 VLMs)
PRIMARY | Capstone spec in this repo |  |  | https://github.com/anshu8830/anshu/blob/main/curriculum/09-capstone-ai-software-engineer.md | W13, W14
PRIMARY | Aider repository map (tree-sitter + graph ranking) |  |  | https://aider.chat/docs/repomap.html | W13
PRIMARY | SWE-bench harness |  |  | https://github.com/SWE-bench/SWE-bench | W13
SECONDARY | RouteLLM paper |  |  | https://arxiv.org/abs/2406.18665 | W13
REFERENCE | SWE-bench leaderboards |  |  | https://www.swebench.com/ | W13
PRIMARY | 2027 continuation plan |  |  | https://github.com/anshu8830/anshu/blob/main/curriculum/10-2027-continuation.md | W14